## Master Data-Executive Dashboard
Month | Project / Work Request Name | Budget | Resources | Schedule | Overall Health | Key Messages/Accomplishments' | Milestones | Risk /Issues
JFM-23 | IPT | As per projection | No Open positions | As per Schedule | Green | ▪ Supplier transfer support activities from FMI to Promed. ▪ Critical support Line down issues in IPG and Leads and NCMR activities ▪ DSM Material Characterization Study & FEA Simulation completion ▪ Ontime resource Allocation for Onbase Walk-in request ▪ DSM Transfer - SCS FDA Submission Support ▪ Lubrizol Material Characterization Study & FEA Simulation completion | 1. SCR support - . a.SCR 2021- 120 second source for alumina insulators in IPGs b.SCR 2022-218 Solvent, Vanishing, HFC Trans change.(IPG) c.SCR - 2021-106 Bal weld process change d.SCR 2020-258 Orion Header Mold M1470 update e.SCR#2021-283 Career Boot Tape 2.Surface Area Reports – DSM Transfer - SCS 3.DSM Lifetime Flex report 4.Surface Area reports - Lubrizol Transfer, 5. A 3.7 China Launch | No risks identified
JFM-23 | EU MDR | As per projection | No Open positions | As per Schedule | Green | ▪ Post submission activity for infinity L&E,DRG L&E. ▪ Risk management Support for CRT activity | R&D SE - Post submission activities for DRG LEA, RFA products and EPG Submit responses to BSI Release of CRT for EUMDR models | No Risk/Issues
JFM-23 | GMI | As per projection | No Open positions | As per Schedule | Green | ▪ Feasibility analysis, ▪ Design evaluation ▪ Circuit interaction evaluation for Gemini IPG alternate resistors | ▪ Gemini Alternate Resistor - Initial Feasibility analysis completed | No risks identified
JFM-23 | Mobile Ops Mrkt Expn | As per projection | No Open positions | As per Schedule | Green | • iPhone 14 Series Systems Device Qualification Testing/Report for ORCA • Continuous Device qualification for new devices, BYOD, Onyx, A3.11 and Gemini • Continuous process improvement including protocol creation, revisions, and test methods | ▪ Qualified for systems: iOS iOS 12.5.7, 15.7.5, 16.4, 16.4.1 ▪ Completed A3.7 SDK15 update and iOS 15.7.4 testing ▪ Completed qualifiation testing for iPhone SE3 and 13/14 Series' for A3.11 ▪ Completed device qualifcaiton testing for iPhone 14 Series for ORCA 1.0 ▪ Completed Oahu/SDK16 update testing for ORCA 1.0 | No risks identified
JFM-23 | Mobile Ops- Jupiter | As per projection | No Open positions | As per Schedule | Green | NA | NA | NA
JFM-23 | Mobile Ops - Oahu | As per projection | No Open positions | As per Schedule | Green | iPhone 14 Series Software Device Qualification Testing and Report for ORCA New automated test scripts for Jupiter | Successful completion of Software qualification testing for ORCA application release. | Working overtime to meet deadlines
JFM-23 | ORCA2.0 | As per projection | No Open positions | As per Schedule | Green | ▪ Involvement in Jupiter DV protcol development ▪ Strategy Planning for Jupiter testing of Mobile Ops ORCA Qualification protocol | ▪ Completed charicterization testing relevant to DV protocol release | No risks identified
JFM-23 | Brookyln Bridge | As per projection | No Open positions | As per Schedule | Green | ▪ OneApp UI: baseline development completed, | ▪ Ceres – Citrine : Development in progress for download file service. | No risks identified
JFM-23 | Sapphire | As per projection | No Open positions | As per Schedule | Green | ▪ NSUP US Hermes 2.5 development and testing completed including formal run. | ▪ NSUP OUS Hermes 2.5.1 development and retesting in progress. | No risks identified
JFM-23 | Cloud Ops | As per projection | No Open positions | As per Schedule | Green | ▪ Liase with MS to implement visual alert using Power BI | ▪ Automate persistent grants table cleanup thru Azure Pipelines, ▪ Automate NeuroLogs Cleanup. | No risks identified
JFM-23 | Hercules | As per projection | No Open positions | As per Schedule | Green | ▪ Completed Jupiter tickets& ona App tickets assigned | ▪ OneAPP development in progress | Scheduled internal dev team meeting every day to discuss technical challenges and timelines to overcome the delay of deliverables and also to increase product knowledge.
JFM-23 | CAPEX | As per projection | No Open positions | As per Schedule | Green | ▪ Formal Execution completed for Jupiter functional team and localisation in progress | ▪ Reusable methods developing to support A3.11 and ORCA1.0 &OneApp Mock development in progress | No risks identified
AMJ-23 | EU MDR | As per projection | No Open positions | As per Schedule | Green | 1. Manual verification reports, Trace matrix and associated technical review meeting minutes released for DRG LEA, RFA products and EPGS 2. RTA protocol release, test execution completion and RTA report released and submitted to BSI. 3. R&D inputs provided and CRT released for DRG. | 1. R&D SE - Post submission activities for DRG LEA, RFA products and EPGS 2. Completion of the Real Time Aging (RTA) study – 8 CH BSX and MDT Adapters 3. Submission to BSI - Real Time Aging (RTA) protocol for 4CH DBS Extensions 4. Release of CRT for EUMDR models for DRG Therapy 5. Submit responses to BSI – Infinity Technical Round 1 and Round 2 | No Risk/Issues
AMJ-23 | GMI | As per projection | No Open positions | As per Schedule | Green | 1.Completed Design Evaluation including Feasibility analysis, Electrical/Mechanical interaction analysis, Reliability analysis and Risk assessment for Wolverine alternate resistors. 2.Hybrid Assembly BOM redline created and shared to Scottsdale Manufacturing for Wolverine Characterization build | 1.Alternate resistor parts reviewed and finalized for Wolverine Project 2.Thin and Thick film resistor specs with Wolverine alternate resistors released in windchill | No risks identified
AMJ-23 | IPT | As per projection | No Open positions | As per Schedule | Green | Support in execution of below activities 1. CAPA Support - CAPA 1271982 (IPG set screw material non conformance issues) 2. PFA Derogation support- Review and analyis for the Presence of fluoro substance in all NMD(IPGs, Leads, chargers & accessories) products. 3. EOL support- New/alternate SMT connectors selection for programmer PCB (SMT Hybrid). 4. EOL support- New/alternate Cable Transceiver/Encoder selection for PPGR and IRDA. 5. OGP Smartscope Changes 6. Risk rating group assessment- Trade name review for all NMD(IPGs, Leads, chargers & accessories) products 7.DSM Transfer- DBS FDA Submission Support 8. Lubrizol Transfer FDA Submission Support 9.Ontime resource Allocation for Onbase Walk-in request | 1.. SCR support a.SCR 2022-223 Juno pacific relocation b.SCR 2022-287 Heraeus Pierce Tool Sensor and Slot Location Program 2.Line down avoidance for Cannula Assembly. 3.DSM Transfer - DBS Surface Area Report. 4.Material Characterization & FEA simulation report for DSM Transfer DBS. 5.Material Characterization & FEA simulation report for Lubrizaol Transfer DRG. 6.Rapid programmer plug kit Material spedifcaiton update per supplier's naming convention. 7.Orion RC chaging cabel material spec update per receiving inspection. | No risks identified
AMJ-23 | Mobile Ops Mrkt Expn | As per projection | No Open positions | As per Schedule | Green | • Systems Qualification Testing/Report for Oahu • iPhone 13, 14 and SE3 Systems Device Qualification Testing/Report for A3.11 • A3.7 SDK15 Systems Qualification Testing/Report | Successful completion of system qualification testing for - Oahu - A3.7 (China) - Iphone14 series - A3.11 releases. | No risks identified
AMJ-23 | Mobile Ops- Jupiter | As per projection | No Open positions | As per Schedule | Green | ORCA with SDK-16 (Oahu) Software Qualification Testing and Regression testing & Report Oahu Pre-Release testing activities - iOS Qualification, Pre-Release Functional testing, Configuration testing and reports Artemis Pre-Release testing activities for A3.7 ( China ) - Pre-release testing and report Language verification for ORCA 2.0 (Jupiter) Porting of existing scripts from Ranorex to Python for Artemis | Successful completion of Software qualification testing for - Oahu - A3.7 (China) - Iphone14 series - A3.11 releases. | No risks identified
AMJ-23 | ORCA2.0 | As per projection | No Open positions | As per Schedule | Green | Completed Gemini Regression Dry runs and Formal. Automated Jupiter regression test cases and completed Dry runs. Completed Jupiter regression Formal. Completed Localization regression Formal. Team started to focus on oneApp development. | Artemis -Automation script development for oneapp GEmini -Automation script development for oneapp Npirt performance automation using jmeter Oneapp testing on both android and ios app platform | No risks identified
AMJ-23 | Brookyln Bridge | As per projection | No Open positions | As per Schedule | Green | OneApp UI: Development in progress Ceres – Citrine Completed development for signing and encrypting the files in download file service Working on integrating Styx and Topaz with feature entitlement service. Ceres – One portal Completed new UI and basic integration for Rep mapper in myNeurosphere application. Working on Citrine – new UI and integration with Common approval system. myPal – Survey authoring tool Completed design for backend and frontend. Work in progress for migrating angular version 11 to 15. | Working towards Hercules/Razor program OneApp changes | Ramping up for new resources is getting delayed, due to which client has started checking with other vendors as well. There will be revenue loss.
AMJ-23 | Sapphire | As per projection | No Open positions | As per Schedule | Green | Development work on schedule for CAS, Topaz and Styx Changes.​ Angular 15 upgrade for NSUP US completed and yet to promote to Live.​ Kinematics Video recorder service prototype development completed | Working towards Hercules/Razor program OneApp changes | No risks or issue in this project
AMJ-23 | Cloud Ops | As per projection | No Open positions | As per Schedule | Green | Setup Build pipeline for Syx.API.Model Power BI Dashboard for Patient View MyPath v2.0.8 Release Plan Onyx Production Support MyPath Production Support Updated Privacy Policy in MyPath Staging and Production Updated OUS VC privacy policy for Clinician/Patient in Production |  | No risks or issue in this project
AMJ-23 | Hercules | As per projection | No Open positions | As per Schedule | Green | Jupiter Development. | OneApp JIRA Tickets | Challenege in requirements gathering discussed with Abbott Leads to ensure team delivering it on time with quality
AMJ-23 | CAPEX | As per projection | No Open positions | As per Schedule | Green | Completed Gemini Regression Dry runs and Formal. Automated Jupiter regression test cases and completed Dry runs. Completed Jupiter regression Formal. Completed Localization regression Formal. Team started to focus on oneApp development. | Artemis -Automation script development for oneapp GEmini -Automation script development for oneapp Npirt performance automation using jmeter Oneapp testing on both android and ios app platform | No risks identified

## Master Data-Resource
NMD Program Name | NMD Sub Program Name | Functional Leads / Service Delivery Leads - HCL | Functional Leads / Service Delivery Leads - Abbott | HCL resource | Function | Skills | Location | Onboarding Status | Reason for Offboarding | Offboarding Date | Resource Skill Level | NPD/Sustenance/Operations | Abbott Functions | Training Compliance | Abbott Program Name ( Gemini, Jupiter,EUMDR,Aquarius, etc( | Overall Exp count: 0-5 years | Overall Exp count: 6-10 years | Overall Exp count: 11-15 years | Overall Exp: More than 15 years | Total HCL experience | Total Abbott experience(exact) | Total Abbott experience (Range) | Abbott Projects worked (Previous) | Upskill plan | Skill Details | Target Date for Upskill | Quarter
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Sesha Sai Srikar Pavan Kumar Chongala | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Expert | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Prashanth Muthuram | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Experienced | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saradha Murugavelu | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experienced | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saurabh Pandey | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experienced | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Vineeth Padalakunta | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Entry Level | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal | X |  |  |  | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn & Bridge | Jasvanth | Mary | Aditya Venkatesh Gurusubramanian | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jasvanth Jabez Jeevan David | Software- Digital | Verification - Test Management | India | Onboarded | Resource Active |  | Expert | NPD | V&V | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 18 | 4 | 3-5 years | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jossy John P | Software- Digital | Verification - System Tester | India | Onboarded | Resource Active |  | Experienced | NPD | V&V | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 11 | 3 | 3-5 years | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Omkar Sankaran | Software- Digital | Development - Technical Manager | India | Onboarded | Resource Active |  | Subject Matter Expert | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 22 | 2 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Narmadha Kannan | Software- Digital | Development - C# .Net | India | Offboarding in progress | Attrition | First week of Jun'23 | Expert | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 12 | 2 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Prabhu. Kannan | Software- Digital | Development - Angular UI | India | Offboarded | Resource performance |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Booshan Ganesh Uganandhan | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Vivek Jaiswal | Software- Digital | Development - C# .Net | India | Offboarded | Attrition |  | Expert | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | A Karthik | Software- Digital | Development - C# .Net | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vijayarajan Natarajan | Software- Digital | Techincal Manager - C# .Net | India | Onboarded | Resource Active |  | Expert | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  |  | X | 16 | 2 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Priyadharshini S | Software- Digital | Development - Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1.5 | 1.5 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Pradeep Ramar | Software- Digital | Development - Angular UI | Plano | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1,5 | 1.5 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Chandrashekar Narendra | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vasundhara B | Software- Digital | Development - Xamarin | Plano | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 3.6 | 1.5 | 1-3 years | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Murugeshkumar Thangavel | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Expert | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Pankaj kumar | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | RAKESH KUMAR THATIPAMULA | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Shafiya Sunkesala | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | JFM-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Avijit Laha | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Abhishek Bhagwat Bedre | Software- Digital | Development - C# .Net | India | Offboarding in progress | Attrition | End of May'23 | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | JFM-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Suraj Maharjan | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | JFM-23
Hercules | Jupiter /One App | Nethaji | Mary | Karandev Veppil Jayadev | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | Less than 1 yr | NA | No |  |  | JFM-23
Hercules | Jupiter /One App | Nethaji | Mary | Amit Gupta | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | Less than 1 yr | NA | No |  |  | JFM-23
Hercules | Jupiter /One App | Nethaji | Mary | Umesh | Software- Digital | Devops | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Jupiter/OneApp | X |  |  |  | 1.5 | 1.5 | 1-3 years | NA | No |  |  | JFM-23
Hercules | Jupiter /One App | Nethaji | Mary | Marthula Malyadiri | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Jupiter/OneApp |  | X |  |  | 0.9 | 0.9 | Less than 1 yr | NA | No |  |  | JFM-23
Hercules | One App | Nethaji | Mary | Christoper HandySide | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp | X |  |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No |  |  | JFM-23
Hercules | One App | Nethaji | Mary | Javier | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp | X |  |  |  | 3 | 3 | 3-5 years | NA | No |  |  | JFM-23
Hercules | One App | Nethaji | Mary | Mahendra | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp |  | X |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No |  |  | JFM-23
Hercules | One App | Nethaji | Mary | Carlos | Software- Digital | C# Xamarin | Plano | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp |  | X |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Rubina Masal | Software- Digital | Development - Test Automation | Plano | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter | X |  |  |  | 1.2 | 1.2 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Surekha Aketi | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Aquarius / Jupiter/OneApp |  | X |  |  | 1.1 | 1.1 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Sivashanmugam Chidambaram | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Rekha Siva sankar | Software- Digital | Verification - Test Automation Architect | India | Onboarded | Resource Active |  | Expert | NPD | Automation | Yes | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Raja Sadaraj | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.5 | 1.5 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Girish | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.1 | 1.1 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Manikya Sudha Nukala | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.3 | 1.3 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Snehal | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  | X |  |  | 1.3 | 1.3 | 1-3 years | NA | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Sachina Ramachandra Kotabagi | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No |  |  | JFM-23
CAPEX | One App Test Automation | Nethaji | Dorin | Srinivasan Desikachari . | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No |  |  | JFM-23
Mobile Ops - sustanence | One App | Nethaji | Dorin | Ju Young | Software- Digital | Development | Plano | Onboarded | Resource Active |  | Experienced | NPD | MobileOps | Yes | Jupiter/OneApp |  | X |  |  | 0.6 | 0.6 | 1-3 years | NA | No |  |  | JFM-23
IPT | IPT | Santhana | Matthew Portmann | Elampooranan R | Mechanical | Sustenance | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  | X |  | 6.5 | 3.1 | 3-5 years | Vascular-Equipment support & NMD-TMV | No |  |  | JFM-23
GMI | GMI | Santhana | Matthew Portmann | Dr. Frank Alexander | Electrical | Sustenance | Plano | Offboarded | Attrition | 2023-01-13 | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No |  |  | JFM-23
GMI | GMI | Santhana | Matthew Portmann | Jayaprabakaran Kesavan | Electrical | Sustenance | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 3.5 | 3.5 | 3-5 years | NA | No |  |  | JFM-23
IPT | IPT | Santhana | Matthew Portmann | Santhana | Mechanical | Sustenance | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  |  | X | 10 | 1.5 | 1-3 years | NMD - IPT | No |  |  | JFM-23
IPT | IPT | Santhana | Matthew Portmann | Isaias Antonio Jimenez Mur illo | Mechanical | Sustenance | Costa Rica | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 0.5 | 0.5 | Less than 1 yr | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Raja SN | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 3.4 | 3-5 years | SH-Luer Standards assessment/remediation (ISO 80369) and Process validation NMD - EUMDR & IPT | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Vasilios Svolopoulos | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1 Month | 1 Month | less than 1 year | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | KISHORE PADMANABHA RAO | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 14 | 5 | 3-5 years | NMD - IPT | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Arunkumaran Sivanantham | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No |  |  | JFM-23
IPT | IPT | Santhana | Matthew Portmann | SIVAKUMAR | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 1.5 | 1.5 | 1-3 years | EUMDR | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Prasanna Nandaragi | Software - Embedded | Software Architect | India | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Sushmitha S | Software - Embedded | Software Architect | India | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No |  |  | JFM-23
IPT | IPT | Kishore | Matthew Portmann | ADITYA GOKHALE | Electrical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Raghavendran Sethumadhavan | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 11.7 | 2.2 | 1-3 years | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Senthilkumar Shanmugam | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 15.4 | 2.7 | 1-3 years | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Jayaashree S | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Priyadarshini M | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Uvaisemohammed Amanullah | Systems | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 1 | 1-3 years | NA | No |  |  | JFM-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Meenachi | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1 | 1 | 1-3 years | NA | No |  |  | JFM-23
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Shruti Rattehalli Puttaraju | Software - Embedded | Software Testing | Plano | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No |  |  | JFM-23
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Iffat Farjana | Software - Embedded | Software Testing | Plano | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No |  |  | JFM-23
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Aswani Jaladi | Software - Embedded | Software Testing | Plano | Offboarded | Project Ramp down | 31/01/2023 | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 9 Months | 9 Months | less than 1 year | NA | No |  |  | JFM-23
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Pavani Addagiri | Software - Embedded | Software Testing | Plano | Offboarded | Project Ramp down | 31/03/2023 | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No |  |  | JFM-23
Mobile Ops Mrkt Expn | MobileOps_Sustaining and Market Expansion | Guhan | Dorin | Muhammad Zia | Software - Embedded | Software Testing | Plano | Onboarded | Resource Active | NA | Entry Level | NPD | Others | Yes | MobileOps_Sustaining and Market Expansion | X |  |  |  | 2 | 2.3 | 1-3 years | NA | No |  |  | JFM-23
Mobile Ops Mrkt Expn | MobileOps_Sustaining and Market Expansion | Guhan | Dorin | Paul Mulenga | Software - Embedded | Software Testing | Plano | Offboarded | Attrition | 2023-10-02 | Entry Level | NPD | Others | Yes | MobileOps_Sustaining and Market Expansion | X |  |  |  | 2 | 2 | 1-3 years | NA | No |  |  | JFM-23
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Guhan | Mary | Vijayakumar sethuraman | Software - Embedded | Firmware Testing | India | Onboarded | Resource Active | NA | Experienced | NPD | Automation | Yes | ORCA 2.0 |  |  | X |  | 2.4 | 2.4 | 1-3 years | NA | No |  |  | JFM-23
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Guhan | Mary | Saranya Veerappan | Software - Embedded | Tools development | India | Onboarded | Resource Active | NA | Experienced | NPD | Automation | Yes | ORCA 2.0 |  | X |  |  |  |  | 3-5 years | NA | No |  |  | JFM-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Sesha Sai Srikar Pavan Kumar Chongala | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Expert | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | AMJ-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Prashanth Muthuram | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Experienced | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | AMJ-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saradha Murugavelu | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experienced | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | AMJ-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saurabh Pandey | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experienced | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No |  |  | AMJ-23
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Vineeth Padalakunta | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Entry Level | Operations | Others | Yes | Virtual Clinic - OneApp / myPath / myPal | X |  |  |  | 1 | 1 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn & Bridge | Jasvanth | Mary | Aditya Venkatesh Gurusubramanian | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jasvanth Jabez Jeevan David | Software- Digital | Verification - Test Management | India | Onboarded | Resource Active |  | Expert | NPD | V&V | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 18 | 4 | 3-5 years | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jossy John P | Software- Digital | Verification - System Tester | India | Onboarded | Resource Active |  | Experienced | NPD | V&V | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 11 | 3 | 3-5 years | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Omkar Sankaran | Software- Digital | Development - Technical Manager | India | Onboarded | Resource Active |  | Subject Matter Expert | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 22 | 2 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Narmadha Kannan | Software- Digital | Development - C# .Net | India | Offboarded | Attrition | 2023-05-06 | Expert | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 12 | 2 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Prabhu. Kannan | Software- Digital | Development - Angular UI | India | Offboarded | Resource performance |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Booshan Ganesh Uganandhan | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 1 | 1 | 1-3 years | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Vivek Jaiswal | Software- Digital | Development - C# .Net | India | Offboarded | Attrition | 2022-10-21 | Expert | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 1 | 1 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | A Karthik | Software- Digital | Development - C# .Net | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vijayarajan Natarajan | Software- Digital | Techincal Manager - C# .Net | India | Onboarded | Resource Active |  | Expert | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  |  | X | 16 | 2 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Priyadharshini S | Software- Digital | Development - Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1.5 | 1.5 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Pradeep Ramar | Software- Digital | Development - Angular UI | Plano | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1,5 | 1.5 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Chandrashekar Narendra | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vasundhara B | Software- Digital | Development - Xamarin | Plano | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 3.6 | 1.5 | 1-3 years | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Murugeshkumar Thangavel | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Expert | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Pankaj kumar | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | RAKESH KUMAR THATIPAMULA | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Shafiya Sunkesala | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Avijit Laha | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Abhishek Bhagwat Bedre | Software- Digital | Development - C# .Net | India | Offboarded | Attrition | 2023-05-22 | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Suraj Maharjan | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Hercules | Jupiter /One App | Nethaji | Mary | Karandev Veppil Jayadev | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | Less than 1 yr | NA | No |  |  | AMJ-23
Hercules | Jupiter /One App | Nethaji | Mary | Amit Gupta | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | Less than 1 yr | NA | No |  |  | AMJ-23
Hercules | Jupiter /One App | Nethaji | Mary | Umesh | Software- Digital | Devops | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Jupiter/OneApp | X |  |  |  | 1.5 | 1.5 | 1-3 years | NA | No |  |  | AMJ-23
Hercules | Jupiter /One App | Nethaji | Mary | Marthula Malyadiri | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | Jupiter/OneApp |  | X |  |  | 0.9 | 0.9 | Less than 1 yr | NA | No |  |  | AMJ-23
Hercules | One App | Nethaji | Mary | Christoper HandySide | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp | X |  |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No |  |  | AMJ-23
Hercules | One App | Nethaji | Mary | Javier | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp | X |  |  |  | 3 | 3 | 3-5 years | NA | No |  |  | AMJ-23
Hercules | One App | Nethaji | Mary | Mahendra | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp |  | X |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No |  |  | AMJ-23
Hercules | One App | Nethaji | Mary | Carlos | Software- Digital | C# Xamarin | Plano | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | Yes | OneApp |  | X |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Rubina Masal | Software- Digital | Development - Test Automation | Plano | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter | X |  |  |  | 1.2 | 1.2 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Surekha Aketi | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Aquarius / Jupiter/OneApp |  | X |  |  | 1.1 | 1.1 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Sivashanmugam Chidambaram | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Rekha Siva sankar | Software- Digital | Verification - Test Automation Architect | India | Onboarded | Resource Active |  | Expert | NPD | Automation | Yes | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Raja Sadaraj | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.5 | 1.5 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Girish | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.1 | 1.1 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Manikya Sudha Nukala | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.3 | 1.3 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Snehal | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  | X |  |  | 1.3 | 1.3 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Sachina Ramachandra Kotabagi | Software- Digital | Development - Test Automation | India | Offboarded | Attrition | 2023-07-31 | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Srinivasan Desikachari . | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No |  |  | AMJ-23
Mobile Ops - Sustanence | One App | Nethaji | Dorin | Ju Young | Software- Digital | Development | Plano | Onboarded | Resource Active |  | Experienced | NPD | MobileOps | Yes | Jupiter/OneApp |  | X |  |  | 0.6 | 0.6 | 1-3 years | NA | No |  |  | AMJ-23
IPT | IPT | Santhana | Matthew Portmann | Elampooranan R | Mechanical | Sustenance | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  | X |  | 6.5 | 3.1 | 3-5 years | Vascular-Equipment support & NMD-TMV | No |  |  | AMJ-23
GMI | GMI | Santhana | Matthew Portmann | Dr. Frank Alexander | Electrical | Sustenance | Plano | Offboarded | Attrition | 2023-01-13 | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No |  |  | AMJ-23
GMI | GMI | Santhana | Matthew Portmann | Jayaprabakaran Kesavan | Electrical | Sustenance | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 3.5 | 3.5 | 3-5 years | NA | No |  |  | AMJ-23
IPT | IPT | Santhana | Matthew Portmann | Santhana | Mechanical | Sustenance | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  |  | X | 10 | 1.5 | 1-3 years | NMD - IPT | No |  |  | AMJ-23
IPT | IPT | Santhana | Matthew Portmann | Isaias Antonio Jimenez Mur illo | Mechanical | Sustenance | Costa Rica | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 0.5 | 0.5 | Less than 1 yr | NA | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Raja SN | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 3.4 | 3-5 years | SH-Luer Standards assessment/remediation (ISO 80369) and Process validation NMD - EUMDR & IPT | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Vasilios Svolopoulos | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1 Month | 1 Month | less than 1 year | NA | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | KISHORE PADMANABHA RAO | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 14 | 5 | 3-5 years | NMD - IPT | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Arunkumaran Sivanantham | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No |  |  | AMJ-23
IPT | IPT | Santhana | Matthew Portmann | SIVAKUMAR | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 1.5 | 1.5 | 1-3 years | EUMDR | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Prasanna Nandaragi | Software - Embedded | Software Architect | India | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Sushmitha S | Software - Embedded | Software Architect | India | Offboarded | Project Ramp down | 2023-07-06 | Experienced | NPD | Others | Yes | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No |  |  | AMJ-23
IPT | IPT | Kishore | Matthew Portmann | ADITYA GOKHALE | Electrical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 2 | 2 | 1-3 years | NA | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Raghavendran Sethumadhavan | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 11.7 | 2.2 | 1-3 years | NA | Yes | Doors tool training | Mar'2024 | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Senthilkumar Shanmugam | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 15.4 | 2.7 | 1-3 years | NA | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Jayaashree S | Electrical | Tech file remediation | India | Offboarded | Attrition | 2023-06-30 | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Priyadarshini M | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | yes | Learning ORCAD and PCB design |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Uvaisemohammed Amanullah | Systems | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 1 | 1-3 years | NA | No |  |  | AMJ-23
EU MDR | EU MDR | Kishore | Matthew Portmann | Meenachi | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1 | 1 | 1-3 years | NA | yes | Learning ORCAD and PCB design |  | AMJ-23
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Lava | Mary | Shruti Rattehalli Puttaraju | Software - Embedded | Software Testing | Plano | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No |  |  | AMJ-23
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Lava | Mary | Iffat Farjana | Software - Embedded | Software Testing | Plano | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No |  |  | AMJ-23
Mobile Ops Mrkt Expn | MobileOps_Sustaining and Market Expansion | Lava | Dorin | Muhammad Zia | Software - Embedded | Software Testing | Plano | Onboarded | Resource Active | NA | Entry Level | NPD | Others | Yes | MobileOps_Sustaining and Market Expansion | X |  |  |  | 2 | 2.3 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Lava | Mary | Vijayakumar sethuraman | Software - Embedded | Firmware Testing | India | Offboarding in progress | Project Ramp down | NA | Experienced | NPD | Automation | Yes | ORCA 2.0 |  |  | X |  | 2.4 | 2.4 | 1-3 years | NA | No |  |  | AMJ-23
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Lava | Mary | Saranya Veerappan | Software- Digital | Tools development | India | Onboarded | Resource Active | NA | Experienced | NPD | Automation | Yes | ORCA 2.0 |  | X |  |  |  |  | 3-5 years | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Pavani Addagiri | Software- Digital | Development - Test Automation | India | Offboarded | Project Ramp down | 2023-05-31 | Experienced | NPD | Automation | Yes | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | NA | No |  |  | AMJ-23
BuildOps Laura | BuildOps Laura | Sivaram | Mary | Rudresh | Software- Digital | Scrum Master | Plano | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | Jupiter/One App |  |  | X |  | 0.25 |  | Less than 1 yr | ORCA2.0. Jupiter | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Nerella | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App | X |  |  |  | 1 | 1 | 1-3 years | NA | Yes | Python/ Appium Advanced,MQMS,JIRA,Agile Basics_Basics |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Gourik Kumar Bora | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | Jupiter/One App |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | Yes | MQMS,JIRA,Agile Basics_Basics |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Tullimelli Devika | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | Yes | MQMS,JIRA,Agile Basics_Basics |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Shaik Wasim Akram | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | Yes | MQMS,JIRA,Agile Basics_Basics |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Chitra Vala Ramamoorthy | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | Yes | MQMS,JIRA,Agile Basics_Basics |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Priyanka Aswar | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | Yes | MQMS,JIRA,Agile Basics_Basics |  | AMJ-23
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vaishali Ramasamy | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Prabhagaran | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | James | Software- Digital | Development - Test Automation | India | Offboarded | Attrition | 11th Aug | Entry Level | NPD | Others | Yes | OneAPP | X |  |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | John/John Bruton | Software- Digital | Development - Test Automation | India | Offboarded | Attrition | 19th Aug | Entry Level | NPD | Others | Yes | OneAPP | X |  |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
ORCA 2.0 | One App Test Automation | Nethaji | Dorin | Bryce | Software- Digital | Development - Test Automation | India | Offboarded | Attrition | 24th Aug | Entry Level | NPD | Others | Yes | OneAPP | X |  |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Karthik Nagarajan | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No |  |  | AMJ-23
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Neel Prasad P | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Others | Yes | OneAPP |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | Yes | MQMS,JIRA,Agile Basics_Basics |  | AMJ-23
Note on E68: Was into project only till 31st January, 2023
Note on E71: Was available in Project until 10th February, 2023

## Master Data- Finance
[8 empty] | 2023-01-21 |  | 2023-02-22 |  | 2023-03-23 |  | 2023-04-24 |  | 2023-05-25 |  | 2023-06-28 |  | 2023-07-29 |  | 2023-08-31 |  | 2023-09-02 |  | 2023-10-03 |  | 2023-11-04 |  | 2023-12-06
Remarks | S.No. | Project / Work Request Name | NMD Program Name | SOW period | Final Consolidated SOW Value(Annual) with 3% discount | Budget Consumed till Date | Advance billing/ Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
| 1 | IPT | Sustaining Engineering | Jan'23 - Dec'23 | 647203.4 | 265976.56 | Actual | 42786.7 | 33985.89 | 45105 | 38291.72 | 59009.95 | 44126.27 | 51313 | 38122.94 | 59009.95 | 41518.56 | 56444.3 | 42786.7 | 53878.65 | 27144.48 | 59009.95 |  | 53878.65 |  | 56444.3 |  | 56444.3 |  | 53878.65
| 2 | EU MDR | Sustaining Engineering | Jan'23 - Dec'23 | 1042470.64 | 509211.82 | Actual | 80622.52 | 50032.6 | 73293.2 | 60091.5 | 93746.62 | 73165.16 | 81518.8 | 71639.27 | 93746.62 | 84661.6 | 89670.68 | 92373.86 | 85594.74 | 77247.83 | 93746.62 |  | 85594.74 |  | 89670.68 |  | 89670.68 |  | 85594.74
| 3 | GMI | Sustaining Engineering | Jan'23 - Dec'23 | 132001.6 | 73078.24 | Actual | 5829.12 | 8909.28 | 5299.2 | 5961.6 | 6094.08 | 6855.84 | 5299.2 | 8938.72 | 14388.8 | 13763.2 | 13763.2 | 16763.2 | 13137.6 | 11886.4 | 14389.0576 |  | 13137.8352 |  | 13763.4464 |  | 13763.4464 |  | 13137.8352
| 4 | Mobile Ops - Mrkt Expn | R&D - Software | Jan'23 - Dec'23 | 302652 | 99288 | Actual | 33096 | 33096 | 33096 | 33096 | 33096 | 33096 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 |  | 22596 |  | 22596 |  | 22596
| 5 | Mobile Ops - Jupiter | R&D - Software | May'23 - Oct'23 | 189000 | 0 | Advance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 |  | 31500 |  | 0 |  | 0
| 7 | Mobile Ops - Oahu | R&D - Software | Jan'23-Apr'23 | 119280 | 89460 | Actual | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| 8 | ORCA2.0 | R&D - Software | Jan'23-Sep'23 | 766892 | 445881.75 | Advance | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 76510 | 76510 | 67875 | 67875 | 105125 | 105125 | 48000 | 48000 | 32250 | 32250 | 11250 |  | 0 |  | 0 |  | 0
| 9 | Brookyln Bridge | R&D - Software | Jan'23-Dec'23 | 142560 | 95040 | Advance | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 |  | 11880 |  | 11880 |  | 11880
| 10 | Sapphire | R&D - Software | Jan'23-Dec'23 | 557556 | 371704 | Advance | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 |  | 46463 |  | 46463 |  | 46463
| 11 | Cloud Ops | R&D - Software | Jan'23-Dec'23 | 802200 | 534800 | Advance | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 |  | 66850 |  | 66850 |  | 66850
| 12 | Hercules(Android dev) | R&D - Software | Jan'23-Dec'23 | 1447775 | 759675 | Advance | 46725 | 46725 | 50400 | 50400 | 53550 | 53550 | 88200 | 88200 | 117600 | 117600 | 117600 | 117600 | 142800 | 142800 | 142800 | 142800 | 159600 |  | 164500 |  | 182000 |  | 182000
| 13 | Build ops Laura | R&D - Software | Mar'23-Dec'23 | 201250 | 120750 | Advance | 0 | 0 | 0 | 0 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 |  | 20125 |  | 20125 |  | 20125
| 14 | CAPEX | R&D - Software | Jan'23-Aug'23 | 169912.75 | 169912.75 | Advance | 7875 | 7875 | 15750 | 15750 | 15750 | 15750 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 25595.5 | 25595.5 | 13387.5 | 13387.5 | 0 |  | 0 |  | 0 |  | 0
|  | Total |  |  | 6520753.39 | 3534778.12 |  | 520574.59 | 484264.02 | 526583.65 | 507231.07 | 585011.9 | 550308.52 | 531093.25 | 511663.18 | 582552.62 | 555350.61 | 612535.43 | 604581.01 | 568420.49 | 532088.21 | 554997.1276 | 387851.5 | 522875.2252 | 0 | 523792.4264 | 0 | 509792.4264 | 0 | 502525.2252 | 0
Reference Charts
| Burn down chart | Budget Available | Consumed
6520753.39
| Jan 23 | 6036489.37 | 484264.02
| Feb 23 | 5529258.3 | 507231.07
| Mar 23 | 4978949.78 | 550308.52
| Total Budget | Month | Consumed |  | Burn out
6520753.39
| 6520753.39 | Jan 23 | 484264.02 |  | 484264.02
| 6520753.39 | Feb 23 | 507231.07 |  | 991495.09
| 6520753.39 | Mar 23 | 550308.52 |  | 1541803.61
Project / Work Request Name | PO value ( From Column "E" ) |  | Actual ( from Column "F" ) |  | Next Qrtr Forecast ( Sum of Column "N","P","R" )
IPT | 617845.72 |  | 265976.56 |  | 166767.25
EU MDR | 995183.312 |  | 509211.82 |  | 264936.1
GMI | 126013.8943 |  | 73078.24 |  | 33451.2
Mobile Ops - Mrkt Expn | 288923.4546 |  | 99288 |  | 67788
Mobile Ops - Jupiter | 180426.8034 |  | 0 |  | 63000
Mobile Ops - Digital | 180426.8034 |  | #REF! |  | #REF!
Mobile Ops - Oahu | 113869.3588 |  | 89460 |  | 29820
ORCA2.0 | 732105.1471 |  | 445881.75 |  | 249510
Brookyln Bridge | 136093.3588 |  | 95040 |  | 35640
Sapphire | 532264.8 |  | 371704 |  | 139389
Cloud Ops | 765811.5471 |  | 534800 |  | 200550
Hercules(Android dev) | 1382102.732 |  | 759675 |  | 323400
CAPEX | 162205.605 |  | 169912.75 |  | 91554.75
| Planned ( From row "16" - Sum of all planned ) | Actual ( from row "16" - Sum of all actual )
Jan 23 | 520574.59 | 484264.02
Feb 23 | 526583.65 | 507231.07
Mar 23 | 585011.9 | 550308.52
Apr 23 | 531093.25 | 511663.18
May 23 | 582552.62
Jun 23 | 612535.43
Jul 23 | 568420.49
Aug 23 | 554997.1276
Sep 23 | 522875.2252
Oct 23 | 523792.4264
Nov 23 | 509792.4264
Dec 23 | 502525.2252
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual + Advance - Details in individual comments
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from $ 732,105.15 to 750521 as per new SOW extension with $20000

## Master Data-Program_Metrics
Period | Project / Work Request Name | On-time delivery | Delivered Right the first time | Project status update | Quality of output | Responsiveness | Technical skills | Escalation Management | Average Score (PCSAT) | Remarks
Jul'22 - Dec'22 | IPT | 7 | 6 | 7 | 5 | 7 | 6 | 5 | 6.14 | Received Dec'22
JFM'23 | IPT | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
AMJ'23 | IPT | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Jul'22 - Dec'22 | EU MDR | 7 | 6 | 7 | 5 | 7 | 6 | 7 | 6.43 | Received Dec'22
JFM'23 | EU MDR | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
AMJ'23 | EU MDR | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
JFM'23 | GMI | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
AMJ'23 | GMI | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Jul'22 - Dec'22 | Mobile Ops - Mrkt Expn | 7 | 7 | 7 | 6 | 7 | 6 | 7 | 6.71 | Received Dec'22
JFM'23 | Mobile Ops - Mrkt Expn | NA | NA | NA | NA | NA | NA | NA | NA | Submitted. No feedback yet
AMJ'23 | Mobile Ops - Mrkt Expn | NA | NA | NA | NA | NA | NA | NA | NA | Submitted. No feedback yet
Jul'22 - Dec'22 | Mobile Ops - Oahu | 7 | 7 | 7 | 6 | 7 | 6 | 7 | 6.71 | Received Dec'22.
JFM'23 | Mobile Ops - Oahu | NA | NA | NA | NA | NA | NA | NA | NA | No feedback.Project closed by Apr'23
AMJ'23 | Mobile Ops - Oahu | NA | NA | NA | NA | NA | NA | NA | NA | Project closed by Apr'23
AMJ'23 | Mobile Ops - Jupiter | NA | NA | NA | NA | NA | NA | NA | NA | Project started from May'23. Not initiated yet
Oct'22 - Mar'23 | ORCA2.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
JFM'23 | ORCA2.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23 [Review period : Oct'22-Mar'23]
AMJ'23 | ORCA2.0 | NA | NA | NA | NA | NA | NA | NA | NA | Submitted for new C-code. No feedback yet
JFM-23 | Brookyln Bridge | 7 | 7 | 7 | 7 | 6 | 7 | 6 | 6.71 | Received Mar'23
AMJ-23 | Brookyln Bridge | 7 | 7 | 7 | 7 | 6 | 7 | 6 | 6.71 | Received Mar'23
JFM-23 | Sapphire | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
AMJ-23 | Sapphire | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
JFM-23 | Cloud Ops | 6 | 6 | 6 | 6 | NA | 6 | 7 | 6.17 | Received Apr'23
AMJ-23 | Cloud Ops | 6 | 6 | 6 | 6 | NA | 6 | 7 | 6.17 | Received Apr'23
JFM-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23
AMJ-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23
JFM-23 | CAPEX | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Started in Jan'23
AMJ-23 | CAPEX | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Apr'23
Program Status
Performance Metrics
|  |  | Program Performance and Quality | Filter for month
Chart for program vs Average
|  |  | Program and Performance metrics- Program wise | Filter for program
Chart for Trend

## Master Data - Invoice
| April |  |  | May |  |  | June
| Submitted by HCL | Approved by Abbott | Payment Status | Submitted by HCL | Approved by Abbott | Payment Status | Submitted by HCL | Approved by Abbott | Payment Status
IPT | green | yellow
EU MDR | green | yellow
GMI | green | yellow
Mobile Ops Mrkt Expn | green | yellow
Mobile Ops- Jupiter | green | yellow
Mobile Ops - Oahu | green | yellow
ORCA2.0 | green | yellow
Brookyln Bridge | green | yellow
Sapphire | green | yellow
Cloud Ops | green | yellow
Hercules | green | yellow
CAPEX | green | yellow

## Master Data - Upskilling plan
S.NO | Skill | Functional area | No of resources planned | Quarter
1 | Agile Basics | Devices-SW | 3 | JFM-23
2 | Doors | Devices-SW | 1 | JFM-23
3 | Python | Devices-SW | 0 | JFM-23
4 | Apium | Devices-SW | 0 | JFM-23
5 | Python | Digital | 4 | JFM-23
6 | Apium | Digital | 4 | JFM-23
7 | MQMS | Digital | 21 | JFM-23
8 | JIRA | Digital | 0 | JFM-23
9 | Agile Basics | Digital | 31 | JFM-23

## Sheet1
S.No. | PO | Value |  |  | Budget Consumed till AMJ | Remaining Forecast | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | 4100002476 | 1556740 | IPT | 647203.4 | 238832.08 | 333534.5 | 42786.7 | 33985.89 | 45105 | 38291.72 | 59009.95 | 44126.27 | 51313 | 38122.94 | 59009.95 | 41518.56 | 56444.3 | 42786.7 | 53878.65 | 27144.48 | 59009.95 |  | 53878.65 |  | 56444.3 |  | 56444.3 |  | 53878.65
2 |  |  | EUMDR | 777535 | 431963.99 | 529872.2 | 80622.52 | 50032.6 | 73293.2 | 60091.5 | 93746.62 | 73165.16 | 81518.8 | 71639.27 | 93746.62 | 84661.6 | 89670.68 | 92373.86 | 85594.74 | 77247.83 | 93746.62 |  | 85594.74 |  | 89670.68 |  | 89670.68 |  | 85594.74
3 |  |  | GMI | 132001.6 | 61191.84 | 81329.2208 | 5829.12 | 8909.28 | 5299.2 | 5961.6 | 6094.08 | 6855.84 | 5299.2 | 8938.72 | 14388.8 | 13763.2 | 13763.2 | 16763.2 | 13137.6 | 11886.4 | 14389.0576 |  | 13137.8352 |  | 13763.4464 |  | 13763.4464 |  | 13137.8352
4 | 4100002452 | 1012032 | Mobile Ops - Mrkt Expn | 302652 | 167076 | 135576 | 33096 | 33096 | 33096 | 33096 | 33096 | 33096 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 |  | 22596 |  | 22596 |  | 22596
5 |  |  | Mobile Ops - Jupiter | 189000 | 63000 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 | 31500 |  | 31500 |  | 0 |  | 0
7 |  |  | Mobile Ops - Oahu | 119280 | 119280 | 0 | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
8 |  |  | Cloud Ops 1 | 401100 | 401100 | 401100 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 |  | 66850 |  | 66850 |  | 66850
9 | 4100002429 | 2107505 | ORCA | 766892 | 695391.75 | 91500 | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 76510 | 76510 | 67875 | 67875 | 105125 | 105125 | 48000 | 48000 | 32250 | 32250 | 11250 |  | 0 |  | 0 |  | 0
10 |  |  | Brooklyn Bridge Sustanence | 142560 | 71280 | 71280 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 |  | 11880 |  | 11880 |  | 11880
11 |  |  | Sapphire - Jupiter | 278778 | 278778 | 278778 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 |  | 46463 |  | 46463 |  | 46463
12 |  |  | Hercules-AD | 474075 | 474075 | 973700 | 46725 | 46725 | 50400 | 50400 | 53550 | 53550 | 88200 | 88200 | 117600 | 117600 | 117600 | 117600 | 142800 | 142800 | 142800 | 142800 | 159600 |  | 164500 |  | 182000 |  | 182000
13 |  |  | Hercules-NPD | 445200 | 130929.75 | 38983 | 7875 | 7875 | 15750 | 15750 | 15750 | 15750 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 25595.5 | 25595.5 | 13387.5 | 13387.5 | 0 |  | 0 |  | 0 |  | 0
|  |  |  | Total | 3132898.41 |  | 520574.59 | 484264.02 | 526583.65 | 507231.07 | 564886.9 | 530183.52 | 510968.25 | 491538.18 | 562427.62 | 535225.61 | 592410.43 | 584456.01 | 548295.49 | 511963.21 | 534872.1276 | 367726.5 | 502750.2252 | 0 | 503667.4264 | 0 | 489667.4264 | 0 | 482400.2252 | 0