## Master Data-Executive Dashboard
Month | Project / Work Request Name | Budget | Resources | Schedule | Overall Health | Key Messages/Accomplishments' | Milestones | Risk /Issues | Quality Metrics er | Performance Metrics Re | Training Compliance Jupiter
JFM-23 | IPT | As per projection | No Open positions | As per Schedule |  | Surface Area Reports – DSM Transfer Lubrizol Transfer DSM Lifetime Flex report EMC Coating Change SCR DSM Material Characterization report CO & CA Review – 12 Onbase Resource assignation FMI to Promed – Suture Anchor FMI to Promed – DRG IPG EPOtek – Impact Assessment SCS – Surface Area Report DSM Transfer – DBS Surface Area Report SCR: No of SCR- 16(WIP) Emerging issue: 1(WIP) Material spec update:1(completed) 1(WIP) GMI: 1(WIP) DSM transfer: WIP SCR- (13Nos) A 3.7 China Launch- completed | 1.SCR support 2.Surface Area Reports – DSM Transfer Lubrizol Transfer DSM Lifetime Flex report 3.Emerging issue 4.A 3.7 China Launch | No risks identified | 6.14 | 6.14 | No resources with Training overdue
JFM-23 | EU MDR | As per projection | No Open positions | As per Schedule |  | 1. BSI Response Infinity - Complete 2. DRG STED update - Complete 3. SCS IPG Entropy assessment for 60601-1- Complete 4. IS-1 Pocket Adapter - Characterization Study Report 90960084, (CO# 1076411)- Complete 5. IS-1 Pocket Adapter - DV report, 90982249 (CO# 1097027)- Complete 6. Infinity Manual Verification Report Release - Complete 7. 90606364 - 62304 Compliance report update- Complete | 1. Post Submission Activity completion 2. BSI Response | EPG IEC 60601-1-2 standard EMI/EMC testing (SCS,DBS,DRG) | 6.43 | 6.43 | No resources with Training overdue
JFM-23 | GMI | As per projection | No Open positions | As per Schedule |  | 1. Design Evaluation Slide Deck for Alternate Resistors - Completed 2.Circuit Interaction Evaluation slide deck for alternate alternate resistors - Completed 3.BOM Redline update - Completed 4.Thin film resistor spec update - In Progress | Gemini Alternate Resistor - Initial Feasibility analysis completed | No risks identified | NA | NA | No resources with Training overdue
JFM-23 | Mobile Ops (Sustaining and Market Expansion)(Software and System Testing Work) | As per projection | No Open positions | As per Schedule |  | Continued qualification testing for iOS versions, devices and SDK updates on A3.7 (China), A3.9, A3.11 and ORCA 1.0 Apps. | Qualified for systems: iOS iOS 12.5.6, 15.7.1, 16.1.1 & 16.1.2 Started A3.7 SDK15 update and iOS 15.7.4 testing Completed qualifiation testing for iPhone SE3 and 13/14 Series' for A3.11 Completed device qualifcaiton testing for iPhone 14 Series for ORCA 1.0 Started Oahu/SDK16 update testing for ORCA 1.0 | No risks identified | 6.71 | 6.71 | No resources with Training overdue
JFM-23 | Mobile Ops - Jupiter | As per projection | No Open positions | As per Schedule |  | N/A | N/A | N/A | N/A | N/A | No resources with Training overdue
JFM-23 | Mobile Ops - Oahu(Acquaris Testing) | As per projection | No Open positions | As per Schedule |  | Part of core team for Oahu (Mobile Ops - System). Started qualification testing for Oahu/SDK16 update, updated relevant DVTPs and particiapted in Design Review prep meetings | Started qual testing for Oahu/SDK16 update on PC | Working overtime to meet deadlines | 6.71 | 6.71 | No resources with Training overdue
JFM-23 | ORCA2.0+FW+FWTest(Gemini / Jupiter Devops & Automation) | As per projection | No Open positions | As per Schedule |  | Assisted in the development of the Jupiter DV protocol and started planning strategy to implement Jupiter testing to Mobile Ops ORCA qualification protocol. | Completed charicterization testing relevant to DV protocol release | No risks identified | 7 | 7 | No resources with Training overdue
JFM-23 | Brookyln Bridge | As per projection | No Open positions | As per Schedule |  | OneApp UI: baseline development completed, - Common Portal: baseline coding standards and implementation model published, | Ceres – Citrine : Development in progress for download file service. | No risks identified | 6.71 | 6.71 | No resources with Training overdue
JFM-23 | Sapphire | As per projection | No Open positions | As per Schedule |  | NSUP US Hermes 2.5 development and testing completed including formal run. | NSUP OUS Hermes 2.5.1 development and retesting in progress. - Styx design work in progress. | No risks identified | 7 | 7 | No resources with Training overdue
JFM-23 | Cloud Ops | As per projection | No Open positions | As per Schedule |  | Liase with MS to implement visual alert using Power BI | Automate persistent grants table cleanup thru Azure Pipelines, - Automate NeuroLogs Cleanup. | No risks identified | 6.17 | 6.17 | No resources with Training overdue
JFM-23 | Hercules | As per projection | No Open positions | As per Schedule |  | Completed Jupiter tickets. Completed OneApp tickets. Issue fixed on both Artemis 3.11 and ORCA 2.0. Completed the Translations of Artemis 3.11 and ORCA 2.0. | OneAPP development in progress | Scheduled internal dev team meeting every day to discuss technical challenges and timelines to overcome the delay of deliverables and also to increase product knowledge. | NA | NA | No resources with Training overdue
JFM-23 | CAPEX | As per projection | No Open positions | As per Schedule |  | 1. Formal Execution completed for Jupiter functional team. • Developed and Executed 127 test cases for Jupiter Features. • Developed and Executed 5 testcases for ORCA1_toJupiter. • Executed 64 test cases for ORCA1_Regression. 2. Developing Test Step Definition files for ORCA1_toJupiter. 3. Formal Execution start from May 2nd for Localization team. • Total CP – 8 and PC – 7 scripts test cases for ..26 CP languages and 28 PC languages. | • Reusable methods developing to support A3.11 and ORCA1.0 • OneApp Mock development | No risks identified | 7 | 7 | No resources with Training overdue
Note on B6: Project starts frm 1st May, 2023

## Master Data-Resource
NMD Program Name | NMD Sub Program Name | Functional Leads / Service Delivery Leads - HCL | Functional Leads / Service Delivery Leads - Abbott | HCL resource | Function | Skills | Location | Onboarding Status | Reason for Offboarding | Offboarding Date | Resource Skill Level | NPD/Sustenance/Operations | Abbott Functions | Training Compliance | Abbott Program Name ( Gemini, Jupiter,EUMDR,Aquarius, etc( | Overall Exp count: 0-5 years | Overall Exp count: 6-10 years | Overall Exp count: 11-15 years | Overall Exp: More than 15 years | Total HCL experience | Total Abbott experience(exact) | Total Abbott experience (Range) | Abbott Projects worked (Previous) | Upskill plan | Skill Details | Target Date for Upskill
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Sesha Sai Srikar Pavan Kumar Chongala | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Expert | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Prashanth Muthuram | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Experianced | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saradha Murugavelu | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experianced | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saurabh Pandey | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experianced | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Vineeth Padalakunta | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Entry Level | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal | X |  |  |  | 1 | 1 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn & Bridge | Jasvanth | Mary | Aditya Venkatesh Gurusubramanian | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jasvanth Jabez Jeevan David | Software- Digital | Verification - Test Management | India | Onboarded | Resource Active |  | Expert | NPD | V&V | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 18 | 4 | 3-5 years | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jossy John P | Software- Digital | Verification - System Tester | India | Onboarded | Resource Active |  | Experianced | NPD | V&V | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 11 | 3 | 3-5 years | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Omkar Sankaran | Software- Digital | Development - Technical Manager | India | Onboarded | Resource Active |  | Subject Matter Expert | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 22 | 2 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Narmadha Kannan | Software- Digital | Development - C# .Net | India | Offboarding in progress | Attrition | First week of Jun'23 | Expert | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 12 | 2 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Prabhu. Kannan | Software- Digital | Development - Angular UI | India | Offboarded | Resource performance |  | Experianced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Booshan Ganesh Uganandhan | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experianced | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 1 | 1 | 1-3 years | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Vivek Jaiswal | Software- Digital | Development - C# .Net | India | Offboarded | Attrition |  | Expert | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 1 | 1 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | A Karthik | Software- Digital | Development - C# .Net | India | Onboarded | Resource Active |  | Experianced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vijayarajan Natarajan | Software- Digital | Techincal Manager - C# .Net | India | Onboarded | Resource Active |  | Expert | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  |  | X | 16 | 2 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Priyadharshini S | Software- Digital | Development - Xamarin | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1.5 | 1.5 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Pradeep Ramar | Software- Digital | Development - Angular UI | Plano | Onboarded | Resource Active |  | Experianced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1,5 | 1.5 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Chandrashekar Narendra | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experianced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vasundhara B | Software- Digital | Development - Xamarin | Plano | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 3.6 | 1.5 | 1-3 years | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Murugeshkumar Thangavel | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Expert | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Pankaj kumar | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experianced | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | less than 1 year | less than 1 year | less than 1 year | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | RAKESH KUMAR THATIPAMULA | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Shafiya Sunkesala | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Avijit Laha | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Abhishek Bhagwat Bedre | Software- Digital | Development - C# .Net | India | Offboarding in progress | Attrition | End of May'23 | Experianced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Suraj Maharjan | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Experianced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No
Hercules | Jupiter /One App | Nethaji | Mary | Karandev Veppil Jayadev | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | NO | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | Less than 1 yr | NA | No
Hercules | Jupiter /One App | Nethaji | Mary | Amit Gupta | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | NO | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | Less than 1 yr | NA | No
Hercules | Jupiter /One App | Nethaji | Mary | Umesh | Software- Digital | Devops | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | No | Jupiter/OneApp | X |  |  |  | 1.5 | 1.5 | 1-3 years | NA | No
Hercules | Jupiter /One App | Nethaji | Mary | Marthula Malyadiri | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | NO | Jupiter/OneApp |  | X |  |  | 0.9 | 0.9 | Less than 1 yr | NA | No
Hercules | One App | Nethaji | Mary | Christoper HandySide | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | NO | OneApp | X |  |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No
Hercules | One App | Nethaji | Mary | Javier | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | NO | OneApp
Hercules | One App | Nethaji | Mary | Mahendra | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | NO | OneApp |  | X |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No
Hercules | One App | Nethaji | Mary | Carlos | Software- Digital | C# Xamarin | Plano | Onboarded | Resource Active |  | Experianced | NPD | Mobile Development | NO | OneApp |  | X |  |  | 0.6 | 0.6 | Less than 1 yr | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Rubina Masal | Software- Digital | Development - Test Automation | Plano | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Jupiter | X |  |  |  | 1.2 | 1.2 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Surekha Aketi | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Aquarius / Jupiter/OneApp |  | X |  |  | 1.1 | 1.1 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Sivashanmugam Chidambaram | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Rekha Siva sankar | Software- Digital | Verification - Test Automation Architect | India | Onboarded | Resource Active |  | Expert | NPD | Automation | NO | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Raja Sadaraj | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Jupiter/One App |  |  | X |  | 1.5 | 1.5 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Girish | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Jupiter/One App |  |  | X |  | 1.1 | 1.1 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Manikya Sudha Nukala | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Jupiter/One App |  |  | X |  | 1.3 | 1.3 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Snehal | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Jupiter/One App |  | X |  |  | 1.3 | 1.3 | 1-3 years | NA | No
CAPEX | One App Test Automation | Nethaji | Dorin | Sachina Ramachandra Kotabagi | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No
CAPEX | One App Test Automation | Nethaji | Dorin | Srinivasan Desikachari . | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experianced | NPD | Automation | NO | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No
Mobile Ops - Jupiter | One App | Nethaji | Dorin | Ju Young | Software- Digital | Development | Plano | Onboarded | Resource Active |  | Experianced | NPD | MobileOps | NO | Jupiter/OneApp |  | X |  |  | 0.6 | 0.6 | 1-3 years | NA | No
Sustenance | IPT | Santhana | Matthew Portmann | Elampooranan R | Mechanical | Sustenance | India | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  | X |  | 6.5 | 3.1 | 3-5 years | Vascular-Equipment support & NMD-TMV | No
Sustenance | GMI | Santhana | Matthew Portmann | Dr. Frank Alexander | Electrical | Sustenance | Plano | Offboarded | Attrition | 2023-01-13 | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No
Sustenance | GMI | Santhana | Matthew Portmann | Jayaprabakaran Kesavan | Electrical | Sustenance | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 3.5 | 3.5 | 3-5 years | NA | No
Sustenance | IPT | Santhana | Matthew Portmann | Santhana | Systems / Mechanical | Sustenance | Plano | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  |  | X | 10 | 1.5 | 1-3 years | NMD - IPT | No
Sustenance | IPT | Santhana | Matthew Portmann | Isaias Antonio Jimenez Mur illo | Mechanical | Sustenance | Costa Rica | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 0.5 | 0.5 | Less than 1 yr | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Raja SN | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 3.4 | 3-5 years | SH-Luer Standards assessment/remediation (ISO 80369) and Process validation NMD - EUMDR & IPT | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Vasilios Svolopoulos | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1 Month | 1 Month | less than 1 year | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | KISHORE PADMANABHA RAO | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 14 | 5 | 3-5 years | NMD - IPT | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Arunkumaran Sivanantham | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No
Sustenance | IPT | Santhana | Matthew Portmann | SIVAKUMAR | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 1.5 | 1.5 | 1-3 years | EUMDR | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Prasanna Nandaragi | Software - Embedded | Software Architect | India | Onboarded | Resource Active | NA | Experianced | NPD | Others |  | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Sushmitha S | Software - Embedded | Software Architect | India | Onboarded | Resource Active | NA | Experianced | NPD | Others |  | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No
Sustenance | IPT | Kishore | Matthew Portmann | ADITYA GOKHALE | Electrical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 2 | 2 | 1-3 years | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Raghavendran Sethumadhavan | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 11.7 | 2.2 | 1-3 years | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Senthilkumar Shanmugam | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 15.4 | 2.7 | 1-3 years | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Jayaashree S | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Priyadarshini M | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Uvaisemohammed Amanullah | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Experianced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 1 | 1-3 years | NA | No
Sustenance | EU MDR | Kishore | Matthew Portmann | Meenachi | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1 | 1 | 1-3 years | NA | No
Mobile Ops | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Shruti Rattehalli Puttaraju | Software- Digital | Software Testing | Plano | Onboarded | Resource Active | NA | Experianced | NPD | Others | No | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No
Mobile Ops | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Iffat Farjana | Software- Digital | Software Testing | Plano | Onboarded | Resource Active | NA | Experianced | NPD | Others | No | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No
Mobile Ops | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Aswani Jaladi | Software- Digital | Software Testing | Plano | Offboarded | Project Ramp down | NA | Experianced | NPD | Others | No | Mobile Ops- Oahu |  | X |  |  | 9 Months | 9 Months | less than 1 year | NA | No
Mobile Ops | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Pavani Addagiri | Software- Digital | Software Testing | Plano | Offboarded | Resource Active | NA | Experianced | NPD | Others | No | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No
Mobile Ops | MobileOps_Sustaining and Market Expansion | Guhan | Dorin | Muhammad Zia | Software- Digital | Software Testing | Plano | Onboarded | Resource Active | NA | Entry Level | NPD | Others | No | MobileOps_Sustaining and Market Expansion | X |  |  |  | 2 | 2.3 | 1-3 years | NA | No
Mobile Ops | MobileOps_Sustaining and Market Expansion | Guhan | Dorin | Paul Mulenga | Software- Digital | Software Testing | Plano | Offboarded | Attrition | NA | Entry Level | NPD | Others | No | MobileOps_Sustaining and Market Expansion | X |  |  |  | 2 | 2 | 1-3 years | NA | No
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Lava | Mary | Vijayakumar sethuraman | Software-Embedded | Firmware Testing | India | Onboarded | Resource Active | NA | Experianced | NPD | Automation | Yes | ORCA 2.0 |  |  | X |  | 2.4 | 2.4 | 1-3 years | NA | No
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Lava | Mary | Saranya Veerappan | Software-Embedded | Tools development | India | Onboarded | Resource Active | NA | Experianced | NPD | Automation | Yes | ORCA 2.0 |  | X | [5 empty] | NA | No
Note on E68: Was into project only till 31st January, 2023
Note on E71: Was available in Project until 10th February, 2023

## Master Data- Finance
[6 empty] | 2023-01-21 |  | 2023-02-22 |  | 2023-03-23 |  | 2023-04-24 |  | 2023-01-25 |  | 2023-03-28 |  | 2023-04-29 |  | 2023-05-31 |  | 2023-07-02 |  | 2023-08-03 |  | 2023-09-04 |  | 2023-10-06 |  | 2023-11-07 |  | 2023-12-09
S.No. | Project / Work Request Name | NMD Program Name | Final Consolidated SOW Value(Annual) | Budget Consumed till Date | Advance billing/ Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | IPT | Sustaining Engineering | 617845.72 | 146544.63 | Actual | 42973.85 | 42973.85 | 48243.92 | 48243.92 | 55326.86 | 55326.86
2 | EU MDR | Sustaining Engineering | 995183.312 | 151739.04 | Actual | 39582.79 | 39582.79 | 50139.3 | 50139.3 | 62016.95 | 62016.95
3 | GMI | Sustaining Engineering | 126013.8943 | 21726.72 | Actual | 8909.28 | 8909.28 | 5961.6 | 5961.6 | 6855.84 | 6855.84
4 | Mobile Ops (Sustaining and Market Expansion)(Software and System Testing Work) | R&D - Software | 288923.4546 | 29798.4 | Actual | 10243.2 | 9777.6 | 10708.8 | 10708.8 | 9312 | 9312
|  |  |  | 66893.2 | Advance | 36784 | 34995.6 | 16662.4 | 16662.4 | 15235.2 | 15235.2
5 | Mobile Ops - Jupiter | R&D - Software | 180426.8034 | 34764.8 | Advance | 11407.2 | 11407.2 | 10864 | 10864 | 12493.6 | 12493.6
6 | Mobile Ops - Oahu(Acquaris Testing) | R&D - Software | 113869.3588 | 87552 | Actual | 28728 | 28728 | 27360 | 27360 | 31464 | 31464
7 | ORCA2.0+FW+FWTest(Gemini / Jupiter Devops & Automation) | R&D - Software | 732105.1471 | 28791.54 | Advance | 9611.73 | 9611.73 | 9114.12 | 9114.12 | 10065.69 | 10065.69
8 | Brookyln Bridge | R&D - Software | 136093.3588 | 290890.76 | Advance | 94655.01 | 94655.01 | 91734.41 | 91734.41 | 104501.34 | 104501.34
9 | Sapphire | R&D - Software | 532264.8 | 130827.78 | Advance | 42515.1 | 42515.1 | 42192.09 | 42192.09 | 46120.59 | 46120.59
10 | Cloud Ops | R&D - Software | 765811.5471 | 144500.57 | Advance | 47503.05 | 47503.05 | 45241 | 45241 | 51756.52 | 51756.52
11 | Hercules(Android dev) | R&D - Software | 1382102.732 | 142684.78 | Advance | 45123.43 | 45123.43 | 42352.14 | 42352.14 | 55209.21 | 55209.21
12 | CAPEX | R&D - Software | 162205.605 | 129811.22 | Advance | 33598.86 | 33598.86 | 32432.92 | 32432.92 | 63779.44 | 63779.44
Total

## Master Data-Program_Metrics
Month | Project / Work Request Name | On-time delivery | Delivered Right the first time | Project status update | Quality of output | Responsiveness | Technical skills | Escalation Management | Average Score (PCSAT) | Remarks
JFM-23 | IPT | 7 | 6 | 7 | 5 | 7 | 6 | 5 | 6.14 | Received Dec'22. Next PCSAT to be triggered by June'23
JFM-23 | EU MDR | 7 | 6 | 7 | 5 | 7 | 6 | 7 | 6.43
JFM-23 | GMI | NA | NA | NA | NA | NA | NA | NA | NA
JFM-23 | Mobile Ops (Sustaining and Market Expansion)(Software and System Testing Work) | 7 | 7 | 7 | 6 | 7 | 6 | 7 | 6.71
JFM-23 | Mobile Ops - Jupiter | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Apr'23
JFM-23 | Mobile Ops - Oahu(Acquaris Testing) | 7 | 7 | 7 | 6 | 7 | 6 | 7 | 6.71 | Received Dec'22. Next PCSAT to be triggered by June'23
JFM-23 | ORCA2.0+FW+FWTest(Gemini / Jupiter Devops & Automation) | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
JFM-23 | Brookyln Bridge | 7 | 7 | 7 | 7 | 6 | 7 | 6 | 6.71 | Received Mar'23
JFM-23 | Sapphire | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
JFM-23 | Cloud Ops | 6 | 6 | 6 | 6 | NA | 6 | 7 | 6.17 | Received Apr'23
JFM-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23
JFM-23 | CAPEX | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Apr'23
Program Status
Performance Metrics
|  |  | Program Performance and Quality | Filter for month
Chart for program vs Average
|  |  | Program and Performance metrics- Program wise | Filter for program
Chart for Trend

## Master Data- Finance_old
[6 empty] | 2023-01-21 |  | 2023-02-22 |  | 2023-03-23 |  | 2023-04-24 |  | 2023-01-25 |  | 2023-03-28 |  | 2023-04-29 |  | 2023-05-31 |  | 2023-07-02 |  | 2023-08-03 |  | 2023-09-04 |  | 2023-10-06 |  | 2023-11-07 |  | 2023-12-09
S.No. | Project / Work Request Name | NMD Program Name | Final Consolidated SOW Value(Annual) | Budget Consumed till Date | Advance billing/ Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | IPT | Sustaining Engineering | 617845.72 | 146544.63 | Actual | 42973.85 | 42973.85 | 48243.92 | 48243.92 | 55326.86 | 55326.86
2 | EU MDR | Sustaining Engineering | 995183.312 | 151739.04 | Actual | 39582.79 | 39582.79 | 50139.3 | 50139.3 | 62016.95 | 62016.95
3 | GMI | Sustaining Engineering | 126013.8943 | 21726.72 | Actual | 8909.28 | 8909.28 | 5961.6 | 5961.6 | 6855.84 | 6855.84
4 | Mobile Ops (Sustaining and Market Expansion)(Software and System Testing Work) | R&D - Software | 288923.4546 | 29798.4 | Actual | 10243.2 | 9777.6 | 10708.8 | 10708.8 | 9312 | 9312
|  |  |  | 66893.2 | Advance | 36784 | 34995.6 | 16662.4 | 16662.4 | 15235.2 | 15235.2
5 | Mobile Ops - Jupiter | R&D - Software | 180426.8034 | 34764.8 | Advance | 11407.2 | 11407.2 | 10864 | 10864 | 12493.6 | 12493.6
6 | Mobile Ops - Oahu(Acquaris Testing) | R&D - Software | 113869.3588 | 87552 | Actual | 28728 | 28728 | 27360 | 27360 | 31464 | 31464
7 | ORCA2.0+FW+FWTest(Gemini / Jupiter Devops & Automation) | R&D - Software | 732105.1471 | 28791.54 | Advance | 9611.73 | 9611.73 | 9114.12 | 9114.12 | 10065.69 | 10065.69
8 | Brookyln Bridge | R&D - Software | 136093.3588 | 290890.76 | Advance | 94655.01 | 94655.01 | 91734.41 | 91734.41 | 104501.34 | 104501.34
9 | Sapphire | R&D - Software | 532264.8 | 130827.78 | Advance | 42515.1 | 42515.1 | 42192.09 | 42192.09 | 46120.59 | 46120.59
10 | Cloud Ops | R&D - Software | 765811.5471 | 144500.57 | Advance | 47503.05 | 47503.05 | 45241 | 45241 | 51756.52 | 51756.52
11 | Hercules(Android dev) | R&D - Software | 1382102.732 | 142684.78 | Advance | 45123.43 | 45123.43 | 42352.14 | 42352.14 | 55209.21 | 55209.21
12 | CAPEX | R&D - Software | 162205.605 | 129811.22 | Advance | 33598.86 | 33598.86 | 32432.92 | 32432.92 | 63779.44 | 63779.44
Total
Program Summary
| S.No. | NMD Program Name | Budget | Budget Consumed till Date
| 1 | Aquarius | #REF! | 87552
| 2 | Brooklyn | #REF! | #REF!
| 3 | Gemini | #REF! | #REF!
| 4 | Jupiter | #REF! | #REF!
| 5 | Others(Cloud Ops) | #REF! | #REF!
| 6 | Sapphire | 891825.4413 | 166227.29
| 7 | Sustenance | #REF! | #REF!
Overall GDC Summary
Budget | Budget Consumed till Date | 2022-10-22 |  | 2022-11-23 | 2022-12-25 |  | 2023-01-26 |  | 2023-02-27 |  | 2023-03-31 |  | 2023-05-02 |  | 2023-06-03 |  | 2023-07-05 |  | 2023-08-06 |  | 2023-09-07 |  | 2023-10-09 |  | 2023-11-10 |  | 2023-12-12
|  | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
0 | 0 | 236160.67 | 218787 | 236475.11
| Total Budget | Month | Consumed | Burn out
|  | 2022-09-22 |  | 2970692.72
| 2970692.72 | 2022-10-22 | 240000 | 2730692.72
| 2970692.72 | 2022-11-22 | 250000 | 2480692.72
| 2970692.72 | 2022-12-22 | 170000 | 2310692.72
| 2970692.72 | 2023-01-22 | 190000 | 2120692.72
| 2970692.72 | 2023-02-22 | 210000 | 1910692.72