## Master Data-Executive Dashboard
Month | Project / Work Request Name | Budget | Resources | Schedule | Overall Health | Key Messages/Accomplishments' | Milestones | Risk /Issues | Quality Metrics er | Performance Metrics Re | Training Compliance
JFM-23 | IPT | As per projection | No Open positions | As per Schedule | Green | ▪ Supplier transfer support activities from FMI to Promed. ▪ Critical support Line down issues in IPG and Leads and NCMR activities | 1.. SCR support 2..Surface Area Reports – DSM Transfer, Lubrizol Transfer, DSM Lifetime Flex report 3. Emerging issue 4. A 3.7 China Launch | No risks identified | 6.14 | 6.14 | No resources with Training overdue
JFM-23 | EU MDR | As per projection | No Open positions | As per Schedule | Green | ▪ Post submission activity for infinity L&E,DRG L&E. ▪ Risk management Support for CRT activity | 1. Post Submission Activity completion 2. BSI Response | EPG IEC 60601-1-2 standard EMI/EMC testing (SCS,DBS,DRG) | 6.43 | 6.43 | No resources with Training overdue
JFM-23 | GMI | As per projection | No Open positions | As per Schedule | Green | ▪ Feasibility analysis, ▪ Design evaluation ▪ Circuit interaction evaluation for Gemini IPG alternate resistors | ▪ Gemini Alternate Resistor - Initial Feasibility analysis completed | No risks identified | NA | NA | No resources with Training overdue
AMJ-23 | EU MDR | As per projection | No Open positions | As per Schedule | Green | ▪ Post submission activity for infinity L&E,DRG L&E. ▪ Risk management Support for CRT activity ▪ Releasing of Real time ageing report for 8ChAdaptors and DBS Extensions ▪ Releasing of verification report and Verfication summary reports. | ▪ Post submission activity for infinity L&E,DRG L&E. ▪ Risk management Support for CRT activity ▪ Releasing of Real time ageing report for 8ChAdaptors and DBS Extensions ▪ Releasing of verification report and Verfication summary reports. | EPG IEC 60601-1-2 standard EMI/EMC testing (SCS,DBS,DRG) | NA, Triggered in Jul'23, yet to receive the feedback | NA | No resources with Training overdue
AMJ-23 | GMI | As per projection | No Open positions | As per Schedule | Green | Design Evaluation Slide Deck for alternate Resistors - Completed Hybrid Assembly BOM Redline update - Completed | Alternate resistor feasibility analysis, circuit interaction analysis and Risk analysis report presented to cross functional team. Thin film resistor spec update and release in windchill Thick film resistor spec update support and release in windchill | No risks identified | NA, Triggered in Jul'23, yet to receive the feedback | NA | No resources with Training overdue
AMJ-23 | IPT | As per projection | No Open positions | As per Schedule | Green | Support in execution of below activities 1. CAPA Support 2. New EOL Component for SMT Hybrid 3. EOL PPGR and IRDA Cable Transceiver/Encoder 4. OGP Smartscope Changes 5. RFA Product Family / REQ-E-2023-0042 | 1.. SCR support 2.Line down avoidance for Cannula Assembly, Emerging Issues and R&D Justification for the selection of 6173 | No risks identified | NA, Triggered in Jul'23, yet to receive the feedback | NA | No resources with Training overdue

## Master Data-Resource
NMD Program Name | NMD Sub Program Name | Functional Leads / Service Delivery Leads - HCL | Functional Leads / Service Delivery Leads - Abbott | HCL resource | Function | Skills | Location | Onboarding Status | Reason for Offboarding | Offboarding Date | Resource Skill Level | NPD/Sustenance/Operations | Abbott Functions | Training Compliance | Abbott Program Name ( Gemini, Jupiter,EUMDR,Aquarius, etc( | Overall Exp count: 0-5 years | Overall Exp count: 6-10 years | Overall Exp count: 11-15 years | Overall Exp: More than 15 years | Total HCL experience | Total Abbott experience(exact) | Total Abbott experience (Range) | Abbott Projects worked (Previous) | Upskill plan | Skill Details | Target Date for Upskill | Period
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Sesha Sai Srikar Pavan Kumar Chongala | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Expert | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No | Python |  | JFM
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Prashanth Muthuram | Software- Digital | Azure DevOps Engineers | Plano | Onboarded | Resource Active |  | Experienced | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No | Python |  | AMJ
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saradha Murugavelu | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experienced | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No | Python |  | JAS
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Saurabh Pandey | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Experienced | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 2 | 2 | 1-3 years | NA | No | Python |  | OND
Cloud Ops | Cloud Operations & DevOps Support | Jasvanth | Dorin | Vineeth Padalakunta | Software- Digital | Azure DevOps Engineers | India | Onboarded | Resource Active |  | Entry Level | Operations | Others | No | Virtual Clinic - OneApp / myPath / myPal | X |  |  |  | 1 | 1 | 1-3 years | NA | No | Python |  | JFM
Brooklyn Bridge | Brooklyn & Bridge | Jasvanth | Mary | Aditya Venkatesh Gurusubramanian | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No | Python |  | AMJ
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Omkar Sankaran | Software- Digital | Development - Technical Manager | India | Onboarded | Resource Active |  | Subject Matter Expert | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 22 | 2 | 1-3 years | NA | No | Python |  | JAS
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Narmadha Kannan | Software- Digital | Development - C# .Net | India | Offboarding in progress | Attrition | First week of Jun'23 | Expert | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 12 | 2 | 1-3 years | NA | No | Python |  | OND
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Prabhu. Kannan | Software- Digital | Development - Angular UI | India | Offboarded | Resource performance |  | Experienced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No | Python |  | JFM
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Booshan Ganesh Uganandhan | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 1 | 1 | 1-3 years | NA | No | Value Engineering |  | AMJ
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Vivek Jaiswal | Software- Digital | Development - C# .Net | India | Offboarded | Attrition |  | Expert | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 1 | 1 | 1-3 years | NA | No | Value Engineering |  | JAS
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | A Karthik | Software- Digital | Development - C# .Net | India | Onboarded | Resource Active |  | Experienced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No | Value Engineering |  | OND
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vijayarajan Natarajan | Software- Digital | Techincal Manager - C# .Net | India | Onboarded | Resource Active |  | Expert | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  |  | X | 16 | 2 | 1-3 years | NA | No | Value Engineering |  | JFM
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Priyadharshini S | Software- Digital | Development - Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1.5 | 1.5 | 1-3 years | NA | No | Value Engineering |  | AMJ
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Pradeep Ramar | Software- Digital | Development - Angular UI | Plano | Onboarded | Resource Active |  | Experienced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1,5 | 1.5 | 1-3 years | NA | No | Value Engineering |  | JAS
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Chandrashekar Narendra | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | 1 | 1 | 1-3 years | NA | No | Value Engineering |  | OND
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Vasundhara B | Software- Digital | Development - Xamarin | Plano | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | 3.6 | 1.5 | 1-3 years | NA | No | Value Engineering |  | JFM
Hercules | Jupiter /One App | Nethaji | Mary | Umesh | Software- Digital | Devops | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | Jupiter/OneApp | X |  |  |  | 1.5 | 1.5 | 1-3 years | NA | No | Value Engineering |  | AMJ
CAPEX | One App Test Automation | Nethaji | Dorin | Rubina Masal | Software- Digital | Development - Test Automation | Plano | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Jupiter | X |  |  |  | 1.2 | 1.2 | 1-3 years | NA | No | Systems/Mechnical |  | JAS
CAPEX | One App Test Automation | Nethaji | Dorin | Surekha Aketi | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Aquarius / Jupiter/OneApp |  | X |  |  | 1.1 | 1.1 | 1-3 years | NA | No | Systems/Mechnical |  | OND
CAPEX | One App Test Automation | Nethaji | Dorin | Sivashanmugam Chidambaram | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No | Systems/Mechnical |  | JFM
CAPEX | One App Test Automation | Nethaji | Dorin | Rekha Siva sankar | Software- Digital | Verification - Test Automation Architect | India | Onboarded | Resource Active |  | Expert | NPD | Automation | No | Aquarius / Jupiter |  |  | X |  | 2 | 2 | 1-3 years | NA | No | Systems/Mechnical |  | AMJ
CAPEX | One App Test Automation | Nethaji | Dorin | Raja Sadaraj | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Jupiter/One App |  |  | X |  | 1.5 | 1.5 | 1-3 years | NA | No | Systems/Mechnical |  | JAS
CAPEX | One App Test Automation | Nethaji | Dorin | Girish | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Jupiter/One App |  |  | X |  | 1.1 | 1.1 | 1-3 years | NA | No | Systems/Mechnical |  | OND
CAPEX | One App Test Automation | Nethaji | Dorin | Manikya Sudha Nukala | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Jupiter/One App |  |  | X |  | 1.3 | 1.3 | 1-3 years | NA | No | Systems/Mechnical |  | JFM
CAPEX | One App Test Automation | Nethaji | Dorin | Snehal | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Jupiter/One App |  | X |  |  | 1.3 | 1.3 | 1-3 years | NA | No | Systems/Mechnical |  | AMJ
CAPEX | One App Test Automation | Nethaji | Dorin | Sachina Ramachandra Kotabagi | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No | Systems/Mechnical |  | JAS
CAPEX | One App Test Automation | Nethaji | Dorin | Srinivasan Desikachari . | Software- Digital | Development - Test Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Jupiter/One App |  |  | X |  | 1.2 | 1.2 | 1-3 years | HMT | No | Systems/Mechnical |  | OND
Mobile Ops - Jupiter | One App | Nethaji | Dorin | Ju Young | Software- Digital | Development | Plano | Onboarded | Resource Active |  | Experienced | NPD | MobileOps | No | Jupiter/OneApp |  | X |  |  | 0.6 | 0.6 | 1-3 years | NA | No | Systems/Mechnical |  | JFM
GMI | GMI | Santhana | Matthew Portmann | Dr. Frank Alexander | Electrical | Sustenance | Plano | Offboarded | Attrition | 2023-01-13 | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No | Systems/Mechnical |  | AMJ
IPT | IPT | Santhana | Matthew Portmann | Santhana | Mechanical | Sustenance | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  |  | X | 10 | 1.5 | 1-3 years | NMD - IPT | No | Systems/Mechnical |  | JAS
EU MDR | EU MDR | Kishore | Matthew Portmann | Arunkumaran Sivanantham | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1.2 | 1.2 | 1-3 years | NA | No | Systems/Mechnical |  | OND
IPT | IPT | Santhana | Matthew Portmann | SIVAKUMAR | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 1.5 | 1.5 | 1-3 years | EUMDR | No | Systems/Mechnical |  | JFM
EU MDR | EU MDR | Kishore | Matthew Portmann | Prasanna Nandaragi | Software - Embedded | Software Architect | India | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No | Systems/Mechnical |  | AMJ
EU MDR | EU MDR | Kishore | Matthew Portmann | Sushmitha S | Software - Embedded | Software Architect | India | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | NMD EUMDR FW |  |  | X |  | 5 | 1.5 | 1-3 years | NA | No | Systems/Mechnical |  | JAS
IPT | IPT | Kishore | Matthew Portmann | ADITYA GOKHALE | Electrical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 2 | 2 | 1-3 years | NA | No | Systems/Mechnical |  | OND
EU MDR | EU MDR | Kishore | Matthew Portmann | Raghavendran Sethumadhavan | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 11.7 | 2.2 | 1-3 years | NA | No | Systems/Mechnical |  | JFM
EU MDR | EU MDR | Kishore | Matthew Portmann | Senthilkumar Shanmugam | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 15.4 | 2.7 | 1-3 years | NA | No | Systems/Mechnical |  | AMJ
EU MDR | EU MDR | Kishore | Matthew Portmann | Jayaashree S | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | No | Systems/Mechnical |  | JAS
EU MDR | EU MDR | Kishore | Matthew Portmann | Priyadarshini M | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1.8 | 1 | 1-3 years | NA | No | Systems/Mechnical |  | OND
EU MDR | EU MDR | Kishore | Matthew Portmann | Uvaisemohammed Amanullah | Systems | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 1 | 1-3 years | NA | No | Systems/Mechnical |  | JFM
EU MDR | EU MDR | Kishore | Matthew Portmann | Meenachi | Electrical | Tech file remediation | India | Onboarded | Resource Active | NA | Entry Level | Sustenance | PETS( Sustenance) | Yes | EUMDR | X |  |  |  | 1 | 1 | 1-3 years | NA | No | Systems/Mechnical |  | AMJ
Mobile Ops Mrkt Expn | MobileOps_Sustaining and Market Expansion | Guhan | Dorin | Muhammad Zia | Software- Digital | Software Testing | Plano | Onboarded | Resource Active | NA | Entry Level | NPD | Others | Yes | MobileOps_Sustaining and Market Expansion | X |  |  |  | 2 | 2.3 | 1-3 years | NA | No | Systems/Mechnical |  | JAS
Mobile Ops Mrkt Expn | MobileOps_Sustaining and Market Expansion | Guhan | Dorin | Paul Mulenga | Software- Digital | Software Testing | Plano | Offboarded | Attrition | NA | Entry Level | NPD | Others | Yes | MobileOps_Sustaining and Market Expansion | X |  |  |  | 2 | 2 | 1-3 years | NA | No | Systems/Mechnical |  | OND
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Lava | Mary | Vijayakumar sethuraman | Software - Embedded | Firmware Testing | India | Onboarded | Resource Active | NA | Experienced | NPD | Automation | Yes | ORCA 2.0 |  |  | X |  | 2.4 | 2.4 | 1-3 years | NA | No | Systems/Mechnical |  | JFM
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jasvanth Jabez Jeevan David | Software- Digital | Verification - Test Management | India | Onboarded | Resource Active |  | Expert | NPD | V&V | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | 18 | 4 | 3-5 years | NA | No | Python |  | AMJ
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Jossy John P | Software- Digital | Verification - System Tester | India | Onboarded | Resource Active |  | Experienced | NPD | V&V | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  | X |  | 11 | 3 | 3-5 years | NA | No | Python |  | JAS
Hercules | One App | Nethaji | Mary | Javier | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | OneApp | X |  |  |  | 3 | 3 | 3-5 years | NA | No | Value Engineering |  | OND
IPT | IPT | Santhana | Matthew Portmann | Elampooranan R | Mechanical | Sustenance | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  |  | X |  | 6.5 | 3.1 | 3-5 years | Vascular-Equipment support & NMD-TMV | No | Systems/Mechnical |  | JFM
GMI | GMI | Santhana | Matthew Portmann | Jayaprabakaran Kesavan | Electrical | Sustenance | India | Onboarded | Resource Active | NA | Expert | Sustenance | PETS( Sustenance) | Yes | GMI |  |  |  | X | 3.5 | 3.5 | 3-5 years | NA | No | Systems/Mechnical |  | AMJ
EU MDR | EU MDR | Kishore | Matthew Portmann | Raja SN | Mechanical | Tech file remediation | India | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  | X |  |  | 4 | 3.4 | 3-5 years | SH-Luer Standards assessment/remediation (ISO 80369) and Process validation NMD - EUMDR & IPT | No | Systems/Mechnical |  | JAS
EU MDR | EU MDR | Kishore | Matthew Portmann | KISHORE PADMANABHA RAO | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 14 | 5 | 3-5 years | NMD - IPT | No | Systems/Mechnical |  | OND
ORCA 2.0 | ORCA2.0 firmware development/ Automation | Lava | Mary | Saranya Veerappan | Software - Embedded | Tools development | India | Onboarded | Resource Active | NA | Experienced | NPD | Automation | Yes | ORCA 2.0 |  | X |  |  |  |  | 3-5 years | NA | No | Systems/Mechnical |  | JFM
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Murugeshkumar Thangavel | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Expert | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No | Value Engineering |  | AMJ
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Pankaj kumar | Software- Digital | Development - Angular UI | India | Onboarded | Resource Active |  | Experienced | NPD | Others | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  |  |  | X | less than 1 year | less than 1 year | less than 1 year | NA | No | Value Engineering |  | JAS
Sapphire | Sapphire / NSUP | Jasvanth | Mary | RAKESH KUMAR THATIPAMULA | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No | Value Engineering |  | OND
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Shafiya Sunkesala | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No | Value Engineering |  | JFM
Sapphire | Sapphire / NSUP | Jasvanth | Mary | Avijit Laha | Software- Digital | Verification - Selenium Automation | India | Onboarded | Resource Active |  | Experienced | NPD | Automation | No | Virtual Clinic - NeuroSphere User Portal / Topaz |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No | Value Engineering |  | AMJ
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Abhishek Bhagwat Bedre | Software- Digital | Development - C# .Net | India | Offboarding in progress | Attrition | End of May'23 | Experienced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  |  | X |  | less than 1 year | less than 1 year | less than 1 year | NA | No | Value Engineering |  | JAS
Brooklyn Bridge | Brooklyn / OneApp | Jasvanth | Mary | Suraj Maharjan | Software- Digital | Development - C# .Net | Plano | Onboarded | Resource Active |  | Experienced | NPD | Others | No | Virtual Clinic - OneApp / myPath / myPal |  | X |  |  | less than 1 year | less than 1 year | less than 1 year | NA | No | Value Engineering |  | OND
EU MDR | EU MDR | Kishore | Matthew Portmann | Vasilios Svolopoulos | Mechanical | Tech file remediation | Plano | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | EUMDR |  |  |  | X | 1 Month | 1 Month | less than 1 year | NA | No | Systems/Mechnical |  | JFM
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Shruti Rattehalli Puttaraju | Software- Digital | Software Testing | Plano | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No | Systems/Mechnical |  | AMJ
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Iffat Farjana | Software- Digital | Software Testing | Plano | Onboarded | Resource Active | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No | Systems/Mechnical |  | JAS
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Aswani Jaladi | Software- Digital | Software Testing | Plano | Offboarded | Project Ramp down | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 9 Months | 9 Months | less than 1 year | NA | No | Systems/Mechnical |  | OND
Mobile Ops - Oahu | Mobile Ops - Oahu(Acquaris Testing) | Guhan | Mary | Pavani Addagiri | Software- Digital | Software Testing | Plano | Offboarding in progress | Project Ramp down | NA | Experienced | NPD | Others | Yes | Mobile Ops- Oahu |  | X |  |  | 6 Months | 6 Months | less than 1 year | NA | No | Systems/Mechnical |  | JFM
Hercules | Jupiter /One App | Nethaji | Mary | Karandev Veppil Jayadev | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | less than 1 year | NA | No | Value Engineering |  | AMJ
Hercules | Jupiter /One App | Nethaji | Mary | Amit Gupta | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | Aquarius / Jupiter |  | X |  |  | 0.8 | 0.8 | less than 1 year | NA | No | Value Engineering |  | JAS
Hercules | Jupiter /One App | Nethaji | Mary | Marthula Malyadiri | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | Jupiter/OneApp |  | X |  |  | 0.9 | 0.9 | less than 1 year | NA | No | Value Engineering |  | OND
Hercules | One App | Nethaji | Mary | Christoper HandySide | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | OneApp | X |  |  |  | 0.6 | 0.6 | less than 1 year | NA | No | Value Engineering |  | JFM
Hercules | One App | Nethaji | Mary | Mahendra | Software- Digital | C# Xamarin | India | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | OneApp |  | X |  |  | 0.6 | 0.6 | less than 1 year | NA | No | Systems/Mechnical |  | AMJ
Hercules | One App | Nethaji | Mary | Carlos | Software- Digital | C# Xamarin | Plano | Onboarded | Resource Active |  | Experienced | NPD | Mobile Development | No | OneApp |  | X |  |  | 0.6 | 0.6 | less than 1 year | NA | No | Systems/Mechnical |  | JAS
IPT | IPT | Santhana | Matthew Portmann | Isaias Antonio Jimenez Mur illo | Mechanical | Sustenance | Costa Rica | Onboarded | Resource Active | NA | Experienced | Sustenance | PETS( Sustenance) | Yes | IPT |  | X |  |  | 0.5 | 0.5 | less than 1 year | NA | No | Systems/Mechnical |  | OND
Note on E45: Was available in Project until 10th February, 2023
Note on E65: Was into project only till 31st January, 2023

## Master Data- Finance
[8 empty] | 2023-01-21 |  | 2023-02-22 |  | 2023-03-23 |  | 2023-04-24 |  | 2023-05-25 |  | 2023-06-28 |  | 2023-07-29 |  | 2023-08-31 |  | 2023-09-02 |  | 2023-10-03 |  | 2023-11-04 |  | 2023-12-06
Remarks | S.No. | Project / Work Request Name | NMD Program Name | SOW period | Final Consolidated SOW Value(Annual) with 3% discount | Budget Consumed till Date | Advance billing/ Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
| 1 | IPT | Sustaining Engineering | Jan'23 - Dec'23 | 647203.4 | 238832.08 | Actual | 42786.7 | 33985.89 | 45105 | 38291.72 | 59009.95 | 44126.27 | 51313 | 38122.94 | 59009.95 | 41518.56 | 56444.3 | 42786.7 | 53878.65 | 0 | 59009.95 | 0 | 53878.65 | 0 | 56444.3 | 0 | 56444.3 | 0 | 53878.65 | 0
| 2 | EU MDR | Sustaining Engineering | Jan'23 - Dec'23 | 1042470.64 | 431963.99 | Actual | 80622.52 | 50032.6 | 73293.2 | 60091.5 | 93746.62 | 73165.16 | 81518.8 | 71639.27 | 93746.62 | 84661.6 | 89670.68 | 92373.86 | 85594.74 | 0 | 93746.62 | 0 | 85594.74 | 0 | 89670.68 | 0 | 89670.68 | 0 | 85594.74 | 0
| 3 | GMI | Sustaining Engineering | Jan'23 - Dec'23 | 132001.6 | 61191.84 | Actual | 5829.12 | 8909.28 | 5299.2 | 5961.6 | 6094.08 | 6855.84 | 5299.2 | 8938.72 | 14388.8 | 13763.2 | 13763.2 | 16763.2 | 13137.6 | 0 | 14389.0576 | 0 | 13137.8352 | 0 | 13763.4464 | 0 | 13763.4464 | 0 | 13137.8352 | 0
| 4 | Mobile Ops - Mrkt Expn | R&D - Software | Jan'23 - Dec'23 | 302652 | 99288 | Actual | 33096 | 33096 | 33096 | 33096 | 33096 | 33096 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 22596 | 0 | 22596 | 0 | 22596 | 0 | 22596 | 0 | 22596 | 0 | 22596 | 0
| 5 | Mobile Ops - Jupiter | R&D - Software | May'23 - Oct'23 | 189000 | 0 | Advance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31500 | 31500 | 31500 | 31500 | 31500 | 0 | 31500 | 0 | 31500 | 0 | 31500 | 0 | 0 | 0 | 0 | 0
| 7 | Mobile Ops - Oahu | R&D - Software | Jan'23-Apr'23 | 119280 | 89460 | Actual | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 29820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | ORCA2.0 | R&D - Software | Jan'23-Sep'23 | 766892 | 445881.75 | Advance | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 148627.25 | 76510 | 76510 | 67875 | 67875 | 105125 | 105125 | 48000 | 0 | 32250 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Brookyln Bridge | R&D - Software | Jan'23-Dec'23 | 142560 | 71280 | Advance | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 11880 | 0 | 11880 | 0 | 11880 | 0 | 11880 | 0 | 11880 | 0 | 11880 | 0
| 10 | Sapphire | R&D - Software | Jan'23-Dec'23 | 557556 | 278778 | Advance | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 46463 | 0 | 46463 | 0 | 46463 | 0 | 46463 | 0 | 46463 | 0 | 46463 | 0
| 11 | Cloud Ops | R&D - Software | Jan'23-Dec'23 | 802200 | 401100 | Advance | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 66850 | 0 | 66850 | 0 | 66850 | 0 | 66850 | 0 | 66850 | 0 | 66850 | 0
| 12 | Hercules(Android dev) | R&D - Software | Jan'23-Dec'23 | 1447775 | 474075 | Advance | 46725 | 46725 | 50400 | 50400 | 53550 | 53550 | 88200 | 88200 | 117600 | 117600 | 117600 | 117600 | 142800 | 0 | 142800 | 0 | 159600 | 0 | 164500 | 0 | 182000 | 0 | 182000 | 0
| 13 | Build ops Laura | R&D - Software | Mar'23-Dec'23 | 201250 | 80500 | Advance | 0 | 0 | 0 | 0 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 20125 | 0 | 20125 | 0 | 20125 | 0 | 20125 | 0 | 20125 | 0 | 20125 | 0
| 14 | CAPEX | R&D - Software | Jan'23-Aug'23 | 169912.75 | 130929.75 | Advance | 7875 | 7875 | 15750 | 15750 | 15750 | 15750 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 30518.25 | 25595.5 | 0 | 13387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total |  |  | 6520753.39 | 2803280.41 |  | 520574.59 | 484264.02 | 526583.65 | 507231.07 | 585011.9 | 550308.52 | 531093.25 | 511663.18 | 582552.62 | 555350.61 | 612535.43 | 604581.01 | 568420.49 | 0 | 554997.1276 | 0 | 522875.2252 | 0 | 523792.4264 | 0 | 509792.4264 | 0 | 502525.2252 | 0
Reference Charts
| Burn down chart | Budget Available | Consumed
| back | 6520753.39
| 2023-01-01 | 6036489.37 | 484264.02
| 2023-02-01 | 5529258.3 | 507231.07
| 2023-03-01 | 4978949.78 | 550308.52
| Total Budget | Month | Consumed |  | Burn out
6520753.39
| 6520753.39 | Jan 23 | 484264.02 |  | 484264.02
| 6520753.39 | Feb 23 | 507231.07 |  | 991495.09
| 6520753.39 | Mar 23 | 550308.52 |  | 1541803.61
Project / Work Request Name | PO value ( From Column "E" ) |  | Actual ( from Column "F" ) |  | Next Qrtr Forecast ( Sum of Column "N","P","R" )
IPT | 617845.72 |  | 238832.08 |  | 166767.25
EU MDR | 995183.312 |  | 431963.99 |  | 264936.1
GMI | 126013.8943 |  | 61191.84 |  | 33451.2
Mobile Ops - Mrkt Expn | 288923.4546 |  | 99288 |  | 67788
Mobile Ops - Jupiter | 180426.8034 |  | 0 |  | 63000
Mobile Ops - Digital | 180426.8034 |  | #REF! |  | #REF!
Mobile Ops - Oahu | 113869.3588 |  | 89460 |  | 29820
ORCA2.0 | 732105.1471 |  | 445881.75 |  | 249510
Brookyln Bridge | 136093.3588 |  | 71280 |  | 35640
Sapphire | 532264.8 |  | 278778 |  | 139389
Cloud Ops | 765811.5471 |  | 401100 |  | 200550
Hercules(Android dev) | 1382102.732 |  | 474075 |  | 323400
CAPEX | 162205.605 |  | 130929.75 |  | 91554.75
| Planned ( From row "16" - Sum of all planned ) | Actual ( from row "16" - Sum of all actual )
Jan 23 | 520574.59 | 484264.02
Feb 23 | 526583.65 | 507231.07
Mar 23 | 585011.9 | 550308.52
Apr 23 | 531093.25 | 511663.18
May 23 | 582552.62
Jun 23 | 612535.43
Jul 23 | 568420.49
Aug 23 | 554997.1276
Sep 23 | 522875.2252
Oct 23 | 523792.4264
Nov 23 | 509792.4264
Dec 23 | 502525.2252
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual + Advance - Details in individual comments
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from $ 732,105.15 to 750521 as per new SOW extension with $20000

## Master Data - Burn Down
Burn down chart | Budget Available | Consumed
6520753.39
44927 | 6036489.37 | 550308.52
44958 | 5529258.3 | 507231.07
44986 | 4978949.78 | 484264.02

## Master Data-Program_Metrics
Review Period | Project / Work Request Name | On-time delivery | Delivered Right the first time | Project status update | Quality of output | Responsiveness | Technical skills | Escalation Management | Average Score (PCSAT) | Remarks
AMJ'23 | IPT | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
AMJ'23 | EU MDR | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
AMJ'23 | GMI | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
AMJ'23 | Mobile Ops - Mrkt Expn | NA | NA | NA | NA | NA | NA | NA | NA | Submitted. No feedback yet
AMJ'23 | Mobile Ops- Jupiter/Oahu | NA | NA | NA | NA | NA | NA | NA | NA | Project started from May'23. Not initiated yet
AMJ'23 | ORCA2.0 | NA | NA | NA | NA | NA | NA | NA | NA | Submitted for new C-code. No feedback yet
AMJ-23 | Brookyln Bridge | NA | NA | NA | NA | NA | NA | NA | NA | Will be initiated in Sep'23
AMJ-23 | Sapphire / Onyx | NA | NA | NA | NA | NA | NA | NA | NA | Will be initiated in Sep'23
AMJ-23 | Cloud Ops | NA | NA | NA | NA | NA | NA | NA | NA | Will be initiated in Sep'23
AMJ-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23

## ONDC
Project / Work Request Name | PO value ( From Column "E" ) | Actual ( from Column "F" ) | Next Qrtr Forecast ( Sum of Column "N","P","R" )
IPT | 617845.72 | 238832.08 | 166767.25 | Jan'23 - Dec'23
EU MDR | 995183.312 | 431963.99 | 264936.1 | Jan'23 - Dec'23
GMI | 126013.8943 | 61191.84 | 33451.2 | Jan'23 - Dec'23
Mobile Ops - Mrkt Expn | 288923.4546 | 99288 | 67788 | Jan'23 - Dec'23
Mobile Ops - Jupiter | 180426.8034 | 0 | 63000 | May'23 - Oct'23
Mobile Ops - Digital | 180426.8034 | #REF! | #REF! | Jan'23-Apr'23
Mobile Ops - Oahu | 113869.3588 | 89460 | 29820 | Jan'23-Sep'23
ORCA2.0 | 732105.1471 | 445881.75 | 249510 | Jan'23-Dec'23
Brookyln Bridge | 136093.3588 | 71280 | 35640 | Jan'23-Dec'23
Sapphire | 532264.8 | 278778 | 139389 | Jan'23-Dec'23
Cloud Ops | 765811.5471 | 401100 | 200550 | Jan'23-Dec'23
Hercules(Android dev) | 1382102.732 | 474075 | 323400 | Mar'23-Dec'23
CAPEX | 162205.605 | 130929.75 | 91554.75 | Jan'23-Aug'23

## Monthly consumtion sum
date | Planned ( From row "16" - Sum of all planned ) | Actual ( from row "16" - Sum of all actual )
2023-01-01 | 520574.59 | 484264.02
2023-02-01 | 526583.65 | 507231.07
2023-03-01 | 585011.9 | 550308.52
2023-04-01 | 531093.25 | 511663.18
2023-05-01 | 582552.62 | 0
2023-06-01 | 612535.43 | 0
2023-07-01 | 568420.49 | 0
2023-08-01 | 554997.1276 | 0
2023-09-01 | 522875.2252 | 0
2023-10-01 | 523792.4264 | 0
2023-11-01 | 509792.4264 | 0
2023-12-01 | 502525.2252 | 0

## Metrics
Project / Work Request Name | JFM-23 | AMJ-23 | JAS-23 | OND-23 | JFM-24
IPT | 7 | 7 | 7 | 7 | TBI
EU MDR | 7 | 7 | 7 | 7 | TBI
GMI | 7 | 7 | 7 | 7 | TBI
Mobile Ops - Mrkt Expn | 6.71 | 6.71 | 6.71 | 6 | TBI
Mobile Ops- Jupiter/Oahu | NA | NA | 6.14 | NA | TBI
ORCA2.0 | 7 | 7 | 7 | 7 | TBI
Brookyln Bridge | 6.71 | 6.71 | 7 | 7 | TBI
Sapphire / Onyx | 7 | NA | 7 | 7 | TBI
Cloud Ops | 6.5 | NA | 6 | 6 | TBI
Hercules | NA | NA | NA | NA | TBI

## Sheet3
Month | Project / Work Request Name | On-time delivery | Delivered Right the first time | Project status update | Quality of output | Responsiveness | Technical skills | Escalation Management | Average Score (PCSAT) | Remarks
Q1-23 | Brookyln Bridge | 7 | 7 | 7 | 7 | 6 | 7 | 6 | 6.71 | Received Mar'23
Q2-23 | Brookyln Bridge | NA | NA | NA | NA | NA | NA | NA | NA | Will be initiated in Sep'23
Q3-23 | Brookyln Bridge | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
Q4-23 | Brookyln Bridge | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received in Oct'23
Q1-23 | Cloud Ops | 6 | 6 | 6 | 6 | NA | 6 | 6.17 | 6.5 | Received Apr'23
Q2-23 | Cloud Ops | NA | NA | NA | NA | NA | NA | NA | NA | Will be initiated in Sep'23
Q3-23 | Cloud Ops | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | Received Apr'23
Q4-23 | Cloud Ops | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | Received in Oct'23
Q1-23 | EU MDR | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q2-23 | EU MDR | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q3-23 | EU MDR | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q4-23 | EU MDR | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q1-23 | GMI | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q2-23 | GMI | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q3-23 | GMI | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q4-23 | GMI | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q1-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23
Q2-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23
Q3-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23
Q4-23 | Hercules | NA | NA | NA | NA | NA | NA | NA | NA | Started in Jan'23
Q1-23 | IPT | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q2-23 | IPT | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q3-23 | IPT | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q4-23 | IPT | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Aug'23. [Review period : Jan'23-Jun'23]
Q1-23 | Mobile Ops - Mrkt Expn | 7 | 7 | 7 | 6 | 6 | 7 | 7 | 6.71 | Received Sep'23. [Review period : Jan'23-Jun'23]
Q2-23 | Mobile Ops - Mrkt Expn | 7 | 7 | 7 | 6 | 6 | 7 | 7 | 6.71 | Received Sep'23. [Review period : Jan'23-Jun'23]
Q3-23 | Mobile Ops - Mrkt Expn | 7 | 7 | 7 | 6 | 6 | 7 | 7 | 6.71 | Received Sep'23. [Review period : Jan'23-Jun'23]
Q4-23 | Mobile Ops - Mrkt Expn | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | Received Sep'23. [Review period : Jan'23-Jun'23]
Q1-23 | Mobile Ops- Jupiter/Oahu | NA | NA | NA | NA | NA | NA | NA | NA | No feedback.Project closed by Apr'23
Q2-23 | Mobile Ops- Jupiter/Oahu | NA | NA | NA | NA | NA | NA | NA | NA | Project started from May'23. Not initiated yet
Q3-23 | Mobile Ops- Jupiter/Oahu | 6 | 7 | 6 | 5 | 6 | 6 | 7 | 6.14 | Received Nov'23. [Review period : May'23 - Oct'23]
Q4-23 | Mobile Ops- Jupiter/Oahu | NA | NA | NA | NA | NA | NA | NA | NA | Not initiated during Q4-23
Q1-23 | ORCA2.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Oct'23. [Review period : Jan'23-Jun'23]
Q2-23 | ORCA2.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Oct'23. [Review period : Jan'23-Jun'23]
Q3-23 | ORCA2.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Oct'23. [Review period : Jan'23-Jun'23]
Q4-23 | ORCA2.0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Oct'23. [Review period : Jan'23-Jun'23]
Q1-23 | Sapphire / Onyx | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
Q2-23 | Sapphire / Onyx | NA | NA | NA | NA | NA | NA | NA | NA | Will be initiated in Sep'23
Q3-23 | Sapphire / Onyx | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received Mar'23
Q4-23 | Sapphire / Onyx | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Received in Oct'23

## Sheet1
Display in the main background ( Probably Abbott log ) on the quarter for which the overall data is being shown. | In praogess / Clarifcation
“Program health” tab:
“Program health” can be renamed as “Engagement Health” to make it clear that we are speaking on HCL scope of activities. | comleted
Revisit the data on “Key Message & Milestones/Metrics” | In praogess /
Make sure to use better highlighting colors for better visibility of selected Program. | comleted
“Resource utilization” tab:
Training compliance data can be fetched from Abbott SPOC and should be processed for our use – Sivaram to help is getting the needed data. | inprogress
Onboarding status data to be re-visited. | inprogress
Should think of presenting – How soon HCL can complete new resource fulfilments. | clarifcation
Selection of different quarter at individual chart level | inprogress ,clarifcation
Upskilling chart to be populated with all relevant realistic information. | inprogress
“Program Metrics” tab:
PCSAT score data to be re-visited and bring in actual data for last 2 quarters. Scale on Y-axis can be with interval of 1 ( from 1-7) | inprogress (text to updated)
“Financial” tab:
Instead of next qtr forecast – project forecast for entire period ( as per SOW timeline ) | connect to lava (tech)
Display values on the bars for easy visibility of the actual figures. | inprogress
Beside program name on X-axis ( Mention SOW duration ) | inprogress
Clarifcation on next quarter forcast if it has to be taken from advanced billing | clarifcation (Shalini)
In the overall PO burn down – Compare it with planned value also along with realistic consumption. | inprogress
We need to collect data for AMJ to be presented for Client. | inprogress