## Resource experience in skill
Abbott Experience levels | Resource count
0-1 years | 60
1-2 years | 100
2-3 years | 80
> 3 years | 40

## Training Compliance
Row lable | Count of Training Compliance | Count of Training Compliance2
No | 56 | 67.47% | month
Yes | 27 | 32.53%

## Upskilling Plans
Function | Upskilled count
Python | 4
Value engineering | 3
Mechanical | 1

## Resource onboarding status
Row Labels | Count of Onboarding Status
Offboarded | 2
Offboarding in progress | 5
Onboarded | 87
(blank)
Grand Total | 94

## Attrition
Row Labels | Count of Reason for Offboarding
Attrition | 2
Project Change requested | 2
Project Ramp down | 3
Resource Active | 87

## Financial Tracking
S.No. | Project Name | Program Name | Start Date | End Date | PO Value | Budget Consumed | OND Forecast
1 | A3.11 2022 | Aquarius | 2022-01-03 | 2022-12-30 | 472763 | 209498.18 | 42525
5 | AQA_Support | Aquarius | 2022-03-31 | 2022-12-31 | 267750 | 123168 | 120488
6 | BrooklynAndBridge2022-3rdSOW | Brooklyn | 2022-09-01 | 2022-12-31 | 183260 | 141439.13 | 281474.01
10 | GeminiFW2022 | Gemini | 2022-01-01 | 2022-12-31 | 468551 | 180257.04 | 42965
12 | Jupiter2022 | Jupiter | 2022-01-01 | 2022-12-31 | 271443 | 282887.01 | 0
13 | Jupiter2022-2ndSOW | Jupiter | 2022-07-01 | 2022-12-31 | 165280 | 120216.47 | 141334.82
14 | Jupiter2022-2ndSOW-LBE3 | Jupiter | 2022-07-01 | 2022-12-31 | 288988 | 0 | 152825
19 | ABT_NMD_TM_JupiterFW_July22ToDec22 | Jupiter | 2022-07-01 | 2022-12-31 | 382244 | 0 | 55607
7 | Capex2022-2ndSOW | Other | 2022-07-01 | 2022-12-31 | 144887 | 78203.34 | 139584.36
8 | CloudOps2022 | Other | 2022-01-01 | 2022-12-31 | 360850 | 256166.63 | 0
9 | CloudOps2022-2ndSOW | Other | 2022-07-01 | 2022-12-31 | 380100 | 127694.34 | 120049.48
17 | Sapphire2022 | Sapphire | 2022-01-01 | 2022-12-31 | 450000 | 220092.03 | 0
18 | Sapphire2022-2ndSOW | Sapphire | 2022-06-30 | 2022-12-31 | 413419 | 178746.75 | 135609.2
2 | Abbott – NMD – EUMDR Support | Sustenance | 2022-03-31 | 2022-12-31 | 1773013 | 1166297.45 | 437087.82

## Resource experience in abbott
Row Labels | Count of Total Abbott experience (Range)
0-5 years | 20
More than 15 years | 14
11-15 years | 24
6-10 years | 36

## Resource Utilization Across Pro
Row Labels | Count of NMD Program Name
Aquiarius | 3.191%
Brooklyn | 19.15%
Gemini | 9.574%
Janus | 1.064%
ORCA 2.0 | 15.96%
Others | 9.574%
Sapphire | 8.511%
Sapphire | 1.064%
Sustenance | 31.91%
(blank) | 0%

## Resource Utilization Across fun
Row Labels | Count of Function
Electrical | 11.7%
Mechanical | 10.64%
Software - Embedded | 15.96%
Software- Digital | 55.32%
Systems | 5.319%
Systems / Mechanical | 1.064%
(blank) | 0%

## Assets sheet
Abbott NMD Asset Tracker
S.No | Asset type ( Laptop, Mobile Device, NMD Prototype, Others | Item Classification | Item Name | Item Description | Calibration Status | Qty. /Size | Serial number / Part Number | Function | NMD Program Name | NMD Sub Program Name | Present Location of the material | Owner/ Contact | Current Status (Utilised or Unutlised) | Reason for Unutlised | Abbott Manager who sent the asset | Received Date | Invoice Number | Remarks
1 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
2 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
3 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
4 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | Vijayakumar Sethuraman-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
16 |  | Load boards | Load Board |  | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | To be updated | Received from Vishwanath on 13/02/2021
17 |  | Load boards | Load Board | Allows a load to be applied to complete the circuit | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | To be updated | Received from Vishwanath on 13/02/2021
19 |  | Dongle | BLE Dongle | Allows bluetooth connection through computer | Calibrated | 1 | NA | NMD Digital | To be updated | To be updated | Vishwanath-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
20 |  | IPG Gemini | IPG canned device | Pulse Generator for DBS Therapy. To be used for engineering use only | Calibrated | 1 | BGA 559.1 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
21 |  | IPG Gemini | IPG canned device | Pulse Generator for DBS Therapy. To be used for engineering use only | Calibrated | 1 | BGA 497.1 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
26 |  | LEADS | 100103560 Leads - Prototypes | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
27 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
28 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
29 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
30 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
31 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
32 |  | LEADS | Leads | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only and include accessories | Calibrated | 3 | P/N : 100043222 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
33 |  | LEADS | Lead | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only |  | 1 | P/N : 45-0042-03 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
34 |  | Misc | Extension | Not complete - Allows the lead and is connected to the pulse generator |  | 1 | Coiled Extension | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
35 |  | IPG Gemini | IPG canned device | IPG, Gemini |  | 1 | 9021908100 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
36 |  | Dongle | Dongle | Nordic BLE Dongle |  | 4 | 8517620090 | Software - Embedded | Sustenance | IPT | Balaji(2) | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
37 |  | Charger Assembly | Charger Assembly | Charger Assembly, Orion RC with Custom Stand |  | 1 | 9021908100 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
38 |  | Cable | USB Cable | USB-C Cable |  | 1 | 8544422000 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
39 |  | Misc | DAQ Card | National Instruments Multifunction DAQ |  | 1 | 8471809000 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
40 |  | Scout Interface Board | Fixture | Test Fixture, NI Test to Scout Interface |  | 1 | 9031808085 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
41 |  | Scout Interface Board | Fixture | Test Fixture, Scout Interface Board |  | 1 | 9031808085 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
42 |  | Misc | Scope | Oscilloscope 100MHz, 4CH |  | 1 | 9030201000 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
43 |  | Misc | Probes | Probe Master Differential Prope |  | 1 | 9030890100 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
44 |  | Misc | Stopwatch | Extech Stopwatch |  | 1 | 9102910000 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
45 |  | Magnet | Magnet | Magnet, Coated -W/Keeper |  | 1 | 8505110010 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
46 |  | Misc | Resistor | iET Labs Resistance Substiuter |  | 1 | 9030333400 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
47 |  | iPADs | iPAD | Apple iPad Mini 5 |  | 1 | 8471300100 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
48 |  | iPADs | iPAD | Apple iPhone 8 |  | 1 | 8517120050 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
49 |  | iPhones | iPhone 8 | iPhone 8 |  | 2 | MQ6Y2LL/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
50 |  | iPhones | iPhone 8 | iPhone 8 |  | 1 | 3D041LL/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
51 |  | iPhones | iPhone 8 | iPhone 8 |  | 1 | NQ6V21L/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
52 |  | iPADs | iPad Mini 5 | iPad Mini 5 |  | 2 | ML/QW2L1/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
53 |  | IPG Breakout board | Gemini IPG breakout Board | Gemini IPG breakout Board |  | 2 | 90514951 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
54 |  | Charger Breakout board | Gemini Charger Breakout Board | Gemini Charger Breakout Board |  | 4 | 90391644 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
55 |  | Hardware boards | IPG hybrid Assembly | IPG hybrid Assembly |  | 2 | 100173188 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number May be a canned device
56 |  | Charger Assembly | Main PCB Assembly Gemini charger | Main PCB Assembly Gemini charger |  | 4 | G00049227 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
57 |  | HF: PES | PCA, Next Generation PES | PCA, Next Generation PES |  | 4 | 600175501 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
58 |  | Enclosure | Enclosure, Top AP | Enclosure, Top AP |  | 4 | 600196617 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
59 |  | Enclosure | Enclosure, Bottom, AP | Enclosure, Bottom, AP |  | 4 | 600196618 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
60 |  | Enclosure | Top Enclosure, NG PES Controller | Top Enclosure, NG PES Controller |  | 4 | 600196318 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
61 |  | Enclosure | Bottom Enclosure, NG PES Controller | Bottom Enclosure, NG PES Controller |  | 4 | 600196337 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
62 |  | Power supply | ICC Nexergy 50W Power Supply MWA0500128 | ICC Nexergy 50W Power Supply MWA0500128 |  | 4 | CC-002403 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Gnana to confirm quantity
63 |  | HF: PES | PCA, Next Generation PES Controller | PCA, Next Generation PES Controller |  | 4 | 600175502 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
64 |  | Cable | Cable, NG PES | Cable, NG PES |  | 4 | 600196319 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02
65 |  | Display module | Hantronix LCD Display Module | Hantronix LCD Display Module |  | 4 | HDA500PT1-25-IPS | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
66 |  | Cable | DTECM 6ft Cable | DTECM 6ft Cable |  | 4 | DT-5002B | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02
67 |  | J-Link | Debuggers/Emulators | J-Link Base |  | 2 | 8471809000 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
68 |  | Emulator | Debuggers/Emulators | MSP low-Power Microcontrollers |  | 2 | 8471809000 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
69 |  | Emulator | Debuggers/Emulators | J-Link 19 Pin |  | 2 | 8471809000 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
70 |  | IPG Breakout board | Orion RC Breakout Board ENG | Orion RC Breakout Board ENG |  | 5 | 9031909195 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
71 |  | IPG Assembly | IPG Assembly, Orion RC | IPG Assembly, Orion RC |  | 7 | 9021908100 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
72 |  | IPG Breakout board | Orion RC Breakout Board ENG | Orion RC Breakout Board ENG |  | 1 | 90514961(9790) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
73 |  | IPG Assembly | IPG Assembly , Orion RC | IPG Assembly , Orion RC |  | 1 | 90483863(10333) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
74 |  | Emulator | Debuggers/Emulators | TI MSP430 Emulator |  | 1 | Nrf52840(F8;AD;12;1C;EA;59) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02 | Repeated ?
75 |  | Emulato | Debuggers/Emulators | NRF BLE Dongle |  | 1 | MSP-FET(19010155C) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04
76 |  | J-Link | Debuggers/Emulators | J-Link Base(segger) |  | 1 | 8.08.00(50129184) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04
77 |  | Emulator | Debuggers/Emulators | MSP low-Power Microcontrollers |  | 1 | 9678(18060037B) (old) | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 59500370
78 |  | J-Link | Debuggers/Emulators | J-Link Base(segger) |  | 1 | 9681(50130213)(old) | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 59500370
79 |  | Emulator | Debuggers/Emulators | Nordic BLE Dongle |  | 1 | E3:4C:FE:12:64:4C (old) | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04
80 |  | IPG Breakout board | Orion RC Breakout Board ENG | Orion RC Breakout Board ENG |  | 1 | 9869 | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 12222020DM02 | Repeated ?
81 |  | IPG Assembly | IPG Assembly, Orion RC | IPG Assembly, Orion RC |  | 1 | 10334 | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 12222020DM02 | Repeated ?

## Calibration Summary
Row Label | Assets Calibration Count | Prevention Assets Calibration Count
Next 15 Days | 27 | 21
Next 30 Days | 43 | 21
Past due | 1 | 1
Not Applicable | 149 | 177
total | 220 | 220

## programmetrics-11
Month | Program Name | On-time delivery | Delivered Right the first time | Project status update | Quality of output | Responsiveness | Technical skills | Escalation Management | Average Score
2022-12-23 | Brooklyn | 5 | 4 | 7 | 5 | 4 | 7 | 4 | 5.1429
2022-12-24 | Sapphire | 5 | 5 | 7 | 5 | 5 | 7 | 5 | 5.5714
2022-12-25 | Gemini | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
2022-12-26 | Janus | 7 | 7 | 4 | 7 | 7 | 4 | 7 | 6.1429
2022-12-27 | Aquarius | 5 | 4 | 5 | 5 | 4 | 5 | 4 | 4.5714
2022-12-28 | ORCA 2.0 | 5 | 5 | 3 | 5 | 5 | 3 | 5 | 4.4286
2022-12-29 | Operations | 4 | 6 | 6 | 4 | 6 | 6 | 6 | 5.4286
2022-12-30 | Jupiter | 4 | 7 | 7 | 4 | 7 | 7 | 7 | 6.1429
2023-01-01 | Brooklyn | 5 | 4 | 7 | 5 | 4 | 7 | 4 | 5.1429
2023-01-01 | Sapphire | 5 | 5 | 7 | 5 | 5 | 7 | 5 | 5.5714
2023-01-01 | Gemini | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2023-01-01 | Janus | 7 | 7 | 4 | 7 | 7 | 4 | 7 | 6.1429
2023-01-01 | Aquarius | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
2023-01-01 | ORCA 2.0 | 5 | 5 | 3 | 5 | 5 | 3 | 5 | 4.4286
2023-01-01 | Operations | 4 | 6 | 6 | 4 | 6 | 6 | 6 | 5.4286
2023-01-01 | Jupiter | 4 | 7 | 7 | 4 | 7 | 7 | 7 | 6.1429
2023-02-01 | Brooklyn | 5 | 4 | 7 | 5 | 4 | 7 | 4 | 5.1429
2023-02-02 | Sapphire | 5 | 5 | 7 | 5 | 5 | 7 | 5 | 5.5714
2023-02-03 | Gemini | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
2023-02-04 | Janus | 7 | 7 | 4 | 7 | 7 | 4 | 7 | 6.1429
2023-02-05 | Aquarius | 6 | 6 | 6 | 5 | 7 | 7 | 7 | 6.2857
2023-02-06 | ORCA 2.0 | 5 | 5 | 3 | 5 | 5 | 3 | 5 | 4.4286
2023-02-07 | Operations | 4 | 6 | 6 | 4 | 6 | 6 | 6 | 5.4286
2023-02-08 | Jupiter | 4 | 7 | 7 | 4 | 7 | 7 | 7 | 6.1429

## bundown-12
Total Budget | Month | Consumed | Burn out
2900000 |  |  | 2900000
2970692.72 | 2022-10-22 | 240000 | 2730692.72
2970692.72 | 2022-11-22 | 250000 | 2480692.72
2970692.72 | 2022-12-22 | 170000 | 2310692.72
2970692.72 | 2023-01-22 | 190000 | 2120692.72
2970692.72 | 2023-02-22 | 210000 | 1910692.72

## finance-13
[9 empty] | 2022-10-21 |  | 2022-11-21
S.No. | NMD Sub Program Name | Start Date | End Date | NMD Program Name | Budget | Budget Consumed till Date | SoW End Date | Advance billing/ Actual | Oct-2022 Planned | Oct-2022 Actual | Nov-2022 Planned | Nov-2022 Actual
1 | Jupiter2022 | 2022-01-01 | 2022-12-31 | Jupiter | 271443 | 271443 | 2022-12-12 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
2 | CloudOps2022 | 2022-01-01 | 2022-12-31 | Others | 360850 | 256166.63 | 2022-12-13 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
3 | Sapphire2022 | 2022-01-01 | 2022-12-31 | Sapphire | 863419 | 220092.03 | 2022-12-14 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
4 | BrooklynAndBridge2022 | 2022-01-01 | 2022-08-30 | Brooklyn | 844419 | 453967.94 | 2022-12-15 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
5 | CapEx2022 | 2022-01-01 | 2022-08-30 | Others | 299236.875 | 314735.955 | 2022-12-16 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
6 | A3.11 2022 | 2022-01-03 | 2022-12-30 | Aquarius | 472763.1 | 209498.175 | 2022-12-17 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
7 | GeminiFW2022 | 2022-01-01 | 2022-12-31 | Gemini | 468551 | 180257.04 | 2022-12-18 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
8 | JupiterFW2022 | 2022-01-01 | 2022-06-30 | Jupiter | 154081 | 125423.91 | 2022-12-19 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
9 | BrooklynAndBridge2022-2ndSOW | 2022-05-01 | 2022-08-31 | Brooklyn | 448000 | 509134.4 | 2022-12-20 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
10 | Sapphire2022-2ndSOW | 2022-06-30 | 2022-12-31 | Sapphire | 413419 | 178746.75 | 2022-12-21 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
11 | Jupiter2022-2ndSOW | 2022-07-01 | 2022-12-31 | Jupiter | 165280 | 120216.465 | 2022-12-22 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
12 | CloudOps2022-2ndSOW | 2022-07-01 | 2022-12-31 | Others | 380100 | 127694.34 | 2022-12-23 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
13 | Capex2022-2ndSOW | 2022-07-01 | 2022-12-31 | Others | 144886.875 | 78203.34 | 2022-12-24 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
14 | MobileOps_SustAndMtktgExpansion | 2022-07-01 | 2022-12-31 | Others | 129600 | 55678 | 2022-12-25 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
15 | MobileOps_Gemini | 2022-08-01 | 2022-10-31 | Gemini | 141750 |  | 2022-12-26 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
16 | BrooklynAndBridge2022-3rdSOW | 2022-09-01 | 2022-12-31 | Brooklyn | 183260 | 141439.13 | 2022-12-27 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
17 | JupiterFW2022-2 | 2022-07-01 | 2022-12-31 | Jupiter | 222622 | 382244 | 2022-12-28 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
18 | Jupiter2022-2ndSOW-LBE3 | 2022-07-01 | 2022-12-31 | Jupiter | 288987.5 | 0 | 2022-12-29 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
19 | IonicRF | 2022-07-01 | 2022-11-30 | Jupiter | 162750 | 0 | 2022-12-30 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
20 | IPT |  |  | Sustenance | 650811.8 | 485181.22 | 2022-12-31 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
21 | EUMDR |  |  | Sustenance | 1773012.52 | 1355607.495 | 2022-12-31 | Actual | 112937.59 | 102244.31 | 109786.54 | 106842.105
22 | GMI |  |  | Sustenance | 149518.4 | 124494.4 | 2022-12-31 | Actual | 13137.6 | 13137.6 | 12512 | 12512
23 | Onsite Test Support(Mobile Ops) | 2022-03-31 | 2022-12-31 | Sustenance | 129600 | 102704 | 2022-12-31 | Actual | 18740.4 | 17886.8 | 17848 | 17848
24 | AQA Support( A3.11 Aquarius) |  |  | Aquarius | 267750 | 220515.2 | 2022-12-31 | Actual | 42957.6 | 42957.6 | 54454.4 | 52402.4

## finaance14
Month | 2023-01-01 | 2023-01-01 | 2023-02-02 | 2023-02-02 | 2023-03-03 | 2023-03-03 | 2023-04-04 | 2023-04-04 | 2023-05-05 | 2023-05-05 | 2023-06-06 | 2023-06-06
Jupiter2022 | 4607855 | 8331764 | 6508086 | 4975721 | 8003068 | 6788131 | 3418904 | 1821714 | 5262317 | 9884203 | 2148476 | 8865788
CloudOps2022 | 8049697 | 8866829 | 9207755 | 4467992 | 5675703 | 1179170 | 1411534 | 8764407 | 8923577 | 5998694 | 1067388 | 4993868
Sapphire2022 | 1199693 | 4162995 | 8480011 | 6731033 | 7563688 | 9341895 | 8560151 | 7052449 | 5837897 | 6252209 | 7435707 | 7182912
BrooklynAndBridge2022 | 7975441 | 5466922 | 3118050 | 9353273 | 2904153 | 6281260 | 1510810 | 4655909 | 7226340 | 5399594 | 9931445 | 8883370
CapEx2022 | 9236394 | 4079474 | 9407543 | 5570319 | 7176350 | 7369936 | 2946592 | 8300918 | 3312863 | 8543182 | 2874769 | 5907303
A3.11 2022 | 7063236 | 7647225 | 4477287 | 3295088 | 6830777 | 6973338 | 2795999 | 3581907 | 5540009 | 2031069 | 3915811 | 5376054
GeminiFW2022 | 5002779 | 8888542 | 1037837 | 7441800 | 2177750 | 4510310 | 4525287 | 5436476 | 4919878 | 2020525 | 1997791 | 9813984
JupiterFW2022 | 8030356 | 1104242 | 3512997 | 5961556 | 7870763 | 1302360 | 3500482 | 8168478 | 2539137 | 1504874 | 4073253 | 5212337
BrooklynAndBridge2022-2ndSOW | 2258646 | 4462356 | 6518804 | 8942573 | 2713847 | 8834226 | 1119333 | 8161860 | 7456893 | 4744268 | 5645693 | 9095745
Sapphire2022-2ndSOW | 3044461 | 9507611 | 3344262 | 3633083 | 8273956 | 8051622 | 5665309 | 2826671 | 7900551 | 3212946 | 5509397 | 7641296
Jupiter2022-2ndSOW | 1465650 | 4500182 | 6397716 | 7971808 | 9224915 | 5824595 | 9710616 | 4727769 | 3487889 | 6977287 | 2843594 | 9949967
CloudOps2022-2ndSOW | 4101058 | 9434525 | 6931802 | 8068856 | 2431686 | 7763123 | 4240940 | 3500770 | 1401610 | 5679886 | 5255615 | 7318487
Capex2022-2ndSOW | 4756849 | 6803858 | 2472385 | 4994505 | 7330544 | 4891661 | 9089617 | 9902092 | 4474233 | 4634715 | 3688789 | 4088290
MobileOps_SustAndMtktgExpansion | 4185482 | 9860306 | 9367289 | 3732297 | 5185899 | 1318252 | 1822848 | 8603889 | 5525760 | 5020569 | 3055846 | 8955760
MobileOps_Gemini | 4008890 | 2914573 | 2054170 | 3095624 | 3817474 | 2297162 | 9819201 | 1414695 | 5629181 | 4568726 | 8911386 | 8568869
BrooklynAndBridge2022-3rdSOW | 5727093 | 3451698 | 6375788 | 4500799 | 7340770 | 1247726 | 6247672 | 6782842 | 5665787 | 4348554 | 9638931 | 5087990
JupiterFW2022-2 | 5697069 | 2512647 | 5562439 | 7912382 | 2089845 | 1935492 | 6961915 | 4710775 | 5027975 | 6974677 | 3699884 | 2902407
Jupiter2022-2ndSOW-LBE3 | 2514211 | 5938670 | 4488680 | 9108463 | 6512782 | 7495575 | 5331050 | 6314621 | 7953681 | 6362073 | 4372165 | 5577575
IonicRF | 9384951 | 4511448 | 8516935 | 3594788 | 2058631 | 8490764 | 1591623 | 6680041 | 7567985 | 3417267 | 8689352 | 2562931
IPT | 7951381 | 3528965 | 4682091 | 9243402 | 2797239 | 4548387 | 3425485 | 6335772 | 5896816 | 8936618 | 4908852 | 9902940
EUMDR | 1686027 | 3155605 | 3985021 | 8969166 | 9407465 | 3643141 | 8549212 | 1742594 | 7917183 | 3250453 | 6837855 | 8786103
GMI | 3801093 | 2870118 | 6972037 | 3240777 | 4388765 | 1220998 | 5771277 | 7948524 | 8582425 | 7190754 | 2235420 | 9687829
Onsite Test Support(Mobile Ops) | 4669699 | 4035445 | 1944226 | 7779191 | 2193011 | 4542318 | 7931893 | 2815351 | 5528402 | 7140981 | 4055540 | 3040869
AQA Support( A3.11 Aquarius) | 9071425 | 2487780 | 7343466 | 5034931 | 3349846 | 9932783 | 6069422 | 7603634 | 5453831 | 3962048 | 2099632 | 3334997

## Login
user name | password | role
PROG-LEADER | 123456 | 1 | GDC | delivery head
DVP | 123456 | 2 | DVP
user3 | 123456 | 3 | functional leader

## executive-bussiness
Month | Program Name | Budget | Resources | Schedule | Overall Health | Key Messages | Milestones | Risk /Issues | Quality Metrics er | Performance Metrics Re | Training Compliance Jupiter
2022-12-23 | Brooklyn | As per projection | No Open positions | As per Schedule | green | dummy text | dummy text | dummy text | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-24 | Sapphire | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-25 | Gemini | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-26 | Janus | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-27 | Aquarius | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-28 | ORCA 2.0 | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-29 | Operations | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-29 | Operations | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-30 | Jupiter | Under utilised | Open positions Greater than 1 month | Behind Schedule | red | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue