## Resource experience in skill
Abbott Experience levels | Resource count
0-1 years | 60
1-2 years | 100
2-3 years | 80
> 3 years | 40

## Training Compliance
Row lable | Count of Training Compliance | Count of Training Compliance2
No | 56 | 67.47% | month
Yes | 27 | 32.53%

## Upskilling Plans
Function | Upskilled count
Python | 4
Value engineering | 3
Mechanical | 1

## Resource onboarding status
Row Labels | Count of Onboarding Status
Offboarded | 2
Offboarding in progress | 5
Onboarded | 87
(blank)
Grand Total | 94

## Attrition
Row Labels | Count of Reason for Offboarding
Attrition | 2
Project Change requested | 2
Project Ramp down | 3
Resource Active | 87

## Financial Tracking
S.No. | Project Name | Program Name | Start Date | End Date | PO Value | Budget Consumed | OND Forecast
1 | A3.11 2022 | Aquarius | 2022-01-03 | 2022-12-30 | 472763 | 209498.18 | 42525
5 | AQA_Support | Aquarius | 2022-03-31 | 2022-12-31 | 267750 | 123168 | 120488
6 | BrooklynAndBridge2022-3rdSOW | Brooklyn | 2022-09-01 | 2022-12-31 | 183260 | 141439.13 | 281474.01
10 | GeminiFW2022 | Gemini | 2022-01-01 | 2022-12-31 | 468551 | 180257.04 | 42965
12 | Jupiter2022 | Jupiter | 2022-01-01 | 2022-12-31 | 271443 | 282887.01 | 0
13 | Jupiter2022-2ndSOW | Jupiter | 2022-07-01 | 2022-12-31 | 165280 | 120216.47 | 141334.82
14 | Jupiter2022-2ndSOW-LBE3 | Jupiter | 2022-07-01 | 2022-12-31 | 288988 | 0 | 152825
19 | ABT_NMD_TM_JupiterFW_July22ToDec22 | Jupiter | 2022-07-01 | 2022-12-31 | 382244 | 0 | 55607
7 | Capex2022-2ndSOW | Other | 2022-07-01 | 2022-12-31 | 144887 | 78203.34 | 139584.36
8 | CloudOps2022 | Other | 2022-01-01 | 2022-12-31 | 360850 | 256166.63 | 0
9 | CloudOps2022-2ndSOW | Other | 2022-07-01 | 2022-12-31 | 380100 | 127694.34 | 120049.48
17 | Sapphire2022 | Sapphire | 2022-01-01 | 2022-12-31 | 450000 | 220092.03 | 0
18 | Sapphire2022-2ndSOW | Sapphire | 2022-06-30 | 2022-12-31 | 413419 | 178746.75 | 135609.2
2 | Abbott – NMD – EUMDR Support | Sustenance | 2022-03-31 | 2022-12-31 | 1773013 | 1166297.45 | 437087.82

## Resource experience in abbott
Row Labels | Count of Total Abbott experience (Range)
0-5 years | 20
More than 15 years | 14
11-15 years | 24
6-10 years | 36

## Resource Utilization Across Pro
Row Labels | Count of NMD Program Name
Aquiarius | 3.191%
Brooklyn | 19.15%
Gemini | 9.574%
Janus | 1.064%
ORCA 2.0 | 15.96%
Others | 9.574%
Sapphire | 8.511%
Sapphire | 1.064%
Sustenance | 31.91%
(blank) | 0%

## Resource Utilization Across fun
Row Labels | Count of Function
Electrical | 11.7%
Mechanical | 10.64%
Software - Embedded | 15.96%
Software- Digital | 55.32%
Systems | 5.319%
Systems / Mechanical | 1.064%
(blank) | 0%

## Assets sheet
Abbott NMD Asset Tracker
S.No | Asset type ( Laptop, Mobile Device, NMD Prototype, Others | Item Classification | Item Name | Item Description | Calibration Status | Qty. /Size | Serial number / Part Number | Function | NMD Program Name | NMD Sub Program Name | Present Location of the material | Owner/ Contact | Current Status (Utilised or Unutlised) | Reason for Unutlised | Abbott Manager who sent the asset | Received Date | Invoice Number | Remarks
1 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
2 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
3 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
4 |  | iPADs | iPad Mini 4 | Clinician Programmer | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | Vijayakumar Sethuraman-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
16 |  | Load boards | Load Board |  | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | To be updated | Received from Vishwanath on 13/02/2021
17 |  | Load boards | Load Board | Allows a load to be applied to complete the circuit | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | To be updated | Received from Vishwanath on 13/02/2021
19 |  | Dongle | BLE Dongle | Allows bluetooth connection through computer | Calibrated | 1 | NA | NMD Digital | To be updated | To be updated | Vishwanath-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
20 |  | IPG Gemini | IPG canned device | Pulse Generator for DBS Therapy. To be used for engineering use only | Calibrated | 1 | BGA 559.1 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
21 |  | IPG Gemini | IPG canned device | Pulse Generator for DBS Therapy. To be used for engineering use only | Calibrated | 1 | BGA 497.1 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
26 |  | LEADS | 100103560 Leads - Prototypes | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
27 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
28 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
29 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
30 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
31 |  | LEADS | 100103560 Leads - New | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only | Calibrated | 1 | NA | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
32 |  | LEADS | Leads | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only and include accessories | Calibrated | 3 | P/N : 100043222 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
33 |  | LEADS | Lead | Allows electrodes to be connected to the pulse generator. These leads are for engineering use only |  | 1 | P/N : 45-0042-03 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
34 |  | Misc | Extension | Not complete - Allows the lead and is connected to the pulse generator |  | 1 | Coiled Extension | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2019-10-18 | 4102019
35 |  | IPG Gemini | IPG canned device | IPG, Gemini |  | 1 | 9021908100 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
36 |  | Dongle | Dongle | Nordic BLE Dongle |  | 4 | 8517620090 | Software - Embedded | Sustenance | IPT | Balaji(2) | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
37 |  | Charger Assembly | Charger Assembly | Charger Assembly, Orion RC with Custom Stand |  | 1 | 9021908100 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
38 |  | Cable | USB Cable | USB-C Cable |  | 1 | 8544422000 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
39 |  | Misc | DAQ Card | National Instruments Multifunction DAQ |  | 1 | 8471809000 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
40 |  | Scout Interface Board | Fixture | Test Fixture, NI Test to Scout Interface |  | 1 | 9031808085 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
41 |  | Scout Interface Board | Fixture | Test Fixture, Scout Interface Board |  | 1 | 9031808085 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
42 |  | Misc | Scope | Oscilloscope 100MHz, 4CH |  | 1 | 9030201000 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
43 |  | Misc | Probes | Probe Master Differential Prope |  | 1 | 9030890100 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
44 |  | Misc | Stopwatch | Extech Stopwatch |  | 1 | 9102910000 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
45 |  | Magnet | Magnet | Magnet, Coated -W/Keeper |  | 1 | 8505110010 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
46 |  | Misc | Resistor | iET Labs Resistance Substiuter |  | 1 | 9030333400 | Software - Embedded | Sustenance | IPT | HCL-Chennai | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
47 |  | iPADs | iPAD | Apple iPad Mini 5 |  | 1 | 8471300100 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
48 |  | iPADs | iPAD | Apple iPhone 8 |  | 1 | 8517120050 | Software - Embedded | Sustenance | IPT | Balaji-WFH | Balaji Viswanathan |  |  | Matthew Portman | 2021-01-04 | 12222020DM02
49 |  | iPhones | iPhone 8 | iPhone 8 |  | 2 | MQ6Y2LL/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
50 |  | iPhones | iPhone 8 | iPhone 8 |  | 1 | 3D041LL/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
51 |  | iPhones | iPhone 8 | iPhone 8 |  | 1 | NQ6V21L/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
52 |  | iPADs | iPad Mini 5 | iPad Mini 5 |  | 2 | ML/QW2L1/A | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
53 |  | IPG Breakout board | Gemini IPG breakout Board | Gemini IPG breakout Board |  | 2 | 90514951 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
54 |  | Charger Breakout board | Gemini Charger Breakout Board | Gemini Charger Breakout Board |  | 4 | 90391644 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
55 |  | Hardware boards | IPG hybrid Assembly | IPG hybrid Assembly |  | 2 | 100173188 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number May be a canned device
56 |  | Charger Assembly | Main PCB Assembly Gemini charger | Main PCB Assembly Gemini charger |  | 4 | G00049227 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-09-15 | To be filled | Invoice available without number
57 |  | HF: PES | PCA, Next Generation PES | PCA, Next Generation PES |  | 4 | 600175501 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
58 |  | Enclosure | Enclosure, Top AP | Enclosure, Top AP |  | 4 | 600196617 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
59 |  | Enclosure | Enclosure, Bottom, AP | Enclosure, Bottom, AP |  | 4 | 600196618 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
60 |  | Enclosure | Top Enclosure, NG PES Controller | Top Enclosure, NG PES Controller |  | 4 | 600196318 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
61 |  | Enclosure | Bottom Enclosure, NG PES Controller | Bottom Enclosure, NG PES Controller |  | 4 | 600196337 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
62 |  | Power supply | ICC Nexergy 50W Power Supply MWA0500128 | ICC Nexergy 50W Power Supply MWA0500128 |  | 4 | CC-002403 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Gnana to confirm quantity
63 |  | HF: PES | PCA, Next Generation PES Controller | PCA, Next Generation PES Controller |  | 4 | 600175502 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
64 |  | Cable | Cable, NG PES | Cable, NG PES |  | 4 | 600196319 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02
65 |  | Display module | Hantronix LCD Display Module | Hantronix LCD Display Module |  | 4 | HDA500PT1-25-IPS | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02 | Should this be for HF ?
66 |  | Cable | DTECM 6ft Cable | DTECM 6ft Cable |  | 4 | DT-5002B | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-10-08 | CL10042021-02
67 |  | J-Link | Debuggers/Emulators | J-Link Base |  | 2 | 8471809000 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
68 |  | Emulator | Debuggers/Emulators | MSP low-Power Microcontrollers |  | 2 | 8471809000 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
69 |  | Emulator | Debuggers/Emulators | J-Link 19 Pin |  | 2 | 8471809000 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
70 |  | IPG Breakout board | Orion RC Breakout Board ENG | Orion RC Breakout Board ENG |  | 5 | 9031909195 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
71 |  | IPG Assembly | IPG Assembly, Orion RC | IPG Assembly, Orion RC |  | 7 | 9021908100 | Software - Embedded | Gemini | Gemini Firmware | HCL-Chennai | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
72 |  | IPG Breakout board | Orion RC Breakout Board ENG | Orion RC Breakout Board ENG |  | 1 | 90514961(9790) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
73 |  | IPG Assembly | IPG Assembly , Orion RC | IPG Assembly , Orion RC |  | 1 | 90483863(10333) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02
74 |  | Emulator | Debuggers/Emulators | TI MSP430 Emulator |  | 1 | Nrf52840(F8;AD;12;1C;EA;59) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04 | 12222020DM02 | Repeated ?
75 |  | Emulato | Debuggers/Emulators | NRF BLE Dongle |  | 1 | MSP-FET(19010155C) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04
76 |  | J-Link | Debuggers/Emulators | J-Link Base(segger) |  | 1 | 8.08.00(50129184) | Software - Embedded | Gemini | Gemini Firmware | jagadeesan velusamy | Simpson |  |  | Mary | 2021-01-04
77 |  | Emulator | Debuggers/Emulators | MSP low-Power Microcontrollers |  | 1 | 9678(18060037B) (old) | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 59500370
78 |  | J-Link | Debuggers/Emulators | J-Link Base(segger) |  | 1 | 9681(50130213)(old) | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 59500370
79 |  | Emulator | Debuggers/Emulators | Nordic BLE Dongle |  | 1 | E3:4C:FE:12:64:4C (old) | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04
80 |  | IPG Breakout board | Orion RC Breakout Board ENG | Orion RC Breakout Board ENG |  | 1 | 9869 | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 12222020DM02 | Repeated ?
81 |  | IPG Assembly | IPG Assembly, Orion RC | IPG Assembly, Orion RC |  | 1 | 10334 | Software - Embedded | Gemini | Gemini Firmware | Suhair MP - WFH | Suhair MP |  |  | Mary | 2021-01-04 | 12222020DM02 | Repeated ?

## Calibration Summary
Row Label | Assets Calibration Count | Prevention Assets Calibration Count
Next 15 Days | 27 | 21
Next 30 Days | 43 | 21
Past due | 1 | 1
Not Applicable | 149 | 177
total | 220 | 220

## programmetrics-11
Month | Program Name | On-time delivery | Delivered Right the first time | Project status update | Quality of output | Responsiveness | Technical skills | Escalation Management | Average Score
2022-12-23 | Brooklyn | 5 | 4 | 7 | 5 | 4 | 7 | 4 | 5.1429
2022-12-24 | Sapphire | 5 | 5 | 7 | 5 | 5 | 7 | 5 | 5.5714
2022-12-25 | Gemini | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
2022-12-26 | Janus | 7 | 7 | 4 | 7 | 7 | 4 | 7 | 6.1429
2022-12-27 | Aquarius | 5 | 4 | 5 | 5 | 4 | 5 | 4 | 4.5714
2022-12-28 | ORCA 2.0 | 5 | 5 | 3 | 5 | 5 | 3 | 5 | 4.4286
2022-12-29 | Operations | 4 | 6 | 6 | 4 | 6 | 6 | 6 | 5.4286
2022-12-30 | Jupiter | 4 | 7 | 7 | 4 | 7 | 7 | 7 | 6.1429
2023-01-01 | Brooklyn | 5 | 4 | 7 | 5 | 4 | 7 | 4 | 5.1429
2023-01-01 | Sapphire | 5 | 5 | 7 | 5 | 5 | 7 | 5 | 5.5714
2023-01-01 | Gemini | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
2023-01-01 | Janus | 7 | 7 | 4 | 7 | 7 | 4 | 7 | 6.1429
2023-01-01 | Aquarius | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
2023-01-01 | ORCA 2.0 | 5 | 5 | 3 | 5 | 5 | 3 | 5 | 4.4286
2023-01-01 | Operations | 4 | 6 | 6 | 4 | 6 | 6 | 6 | 5.4286
2023-01-01 | Jupiter | 4 | 7 | 7 | 4 | 7 | 7 | 7 | 6.1429
2023-02-01 | Brooklyn | 5 | 4 | 7 | 5 | 4 | 7 | 4 | 5.1429
2023-02-02 | Sapphire | 5 | 5 | 7 | 5 | 5 | 7 | 5 | 5.5714
2023-02-03 | Gemini | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
2023-02-04 | Janus | 7 | 7 | 4 | 7 | 7 | 4 | 7 | 6.1429
2023-02-05 | Aquarius | 6 | 6 | 6 | 5 | 7 | 7 | 7 | 6.2857
2023-02-06 | ORCA 2.0 | 5 | 5 | 3 | 5 | 5 | 3 | 5 | 4.4286
2023-02-07 | Operations | 4 | 6 | 6 | 4 | 6 | 6 | 6 | 5.4286
2023-02-08 | Jupiter | 4 | 7 | 7 | 4 | 7 | 7 | 7 | 6.1429

## bundown-12
Total Budget | Month | Consumed | Burn out
2900000 |  |  | 2900000
2970692.72 | 2022-10-22 | 240000 | 2730692.72
2970692.72 | 2022-11-22 | 250000 | 2480692.72
2970692.72 | 2022-12-22 | 170000 | 2310692.72
2970692.72 | 2023-01-22 | 190000 | 2120692.72
2970692.72 | 2023-02-22 | 210000 | 1910692.72

## finance-13
[9 empty] | 2022-10-21 |  | 2022-11-21
S.No. | NMD Sub Program Name | Start Date | End Date | NMD Program Name | Budget | Budget Consumed till Date | SoW End Date | Advance billing/ Actual | Oct-2022 Planned | Oct-2022 Actual | Nov-2022 Planned | Nov-2022 Actual
1 | Jupiter2022 | 2022-01-01 | 2022-12-31 | Jupiter | 271443 | 271443 | 2022-12-12 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
2 | CloudOps2022 | 2022-01-01 | 2022-12-31 | Others | 360850 | 256166.63 | 2022-12-13 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
3 | Sapphire2022 | 2022-01-01 | 2022-12-31 | Sapphire | 863419 | 220092.03 | 2022-12-14 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
4 | BrooklynAndBridge2022 | 2022-01-01 | 2022-08-30 | Brooklyn | 844419 | 453967.94 | 2022-12-15 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
5 | CapEx2022 | 2022-01-01 | 2022-08-30 | Others | 299236.875 | 314735.955 | 2022-12-16 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
6 | A3.11 2022 | 2022-01-03 | 2022-12-30 | Aquarius | 472763.1 | 209498.175 | 2022-12-17 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
7 | GeminiFW2022 | 2022-01-01 | 2022-12-31 | Gemini | 468551 | 180257.04 | 2022-12-18 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
8 | JupiterFW2022 | 2022-01-01 | 2022-06-30 | Jupiter | 154081 | 125423.91 | 2022-12-19 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
9 | BrooklynAndBridge2022-2ndSOW | 2022-05-01 | 2022-08-31 | Brooklyn | 448000 | 509134.4 | 2022-12-20 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
10 | Sapphire2022-2ndSOW | 2022-06-30 | 2022-12-31 | Sapphire | 413419 | 178746.75 | 2022-12-21 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
11 | Jupiter2022-2ndSOW | 2022-07-01 | 2022-12-31 | Jupiter | 165280 | 120216.465 | 2022-12-22 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
12 | CloudOps2022-2ndSOW | 2022-07-01 | 2022-12-31 | Others | 380100 | 127694.34 | 2022-12-23 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
13 | Capex2022-2ndSOW | 2022-07-01 | 2022-12-31 | Others | 144886.875 | 78203.34 | 2022-12-24 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
14 | MobileOps_SustAndMtktgExpansion | 2022-07-01 | 2022-12-31 | Others | 129600 | 55678 | 2022-12-25 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
15 | MobileOps_Gemini | 2022-08-01 | 2022-10-31 | Gemini | 141750 |  | 2022-12-26 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
16 | BrooklynAndBridge2022-3rdSOW | 2022-09-01 | 2022-12-31 | Brooklyn | 183260 | 141439.13 | 2022-12-27 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
17 | JupiterFW2022-2 | 2022-07-01 | 2022-12-31 | Jupiter | 222622 | 382244 | 2022-12-28 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
18 | Jupiter2022-2ndSOW-LBE3 | 2022-07-01 | 2022-12-31 | Jupiter | 288987.5 | 0 | 2022-12-29 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
19 | IonicRF | 2022-07-01 | 2022-11-30 | Jupiter | 162750 | 0 | 2022-12-30 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
20 | IPT |  |  | Sustenance | 650811.8 | 485181.22 | 2022-12-31 | Actual | 48387.48 | 42560.69 | 41874.17 | 41874.9
21 | EUMDR |  |  | Sustenance | 1773012.52 | 1355607.495 | 2022-12-31 | Actual | 112937.59 | 102244.31 | 109786.54 | 106842.105
22 | GMI |  |  | Sustenance | 149518.4 | 124494.4 | 2022-12-31 | Actual | 13137.6 | 13137.6 | 12512 | 12512
23 | Onsite Test Support(Mobile Ops) | 2022-03-31 | 2022-12-31 | Sustenance | 129600 | 102704 | 2022-12-31 | Actual | 18740.4 | 17886.8 | 17848 | 17848
24 | AQA Support( A3.11 Aquarius) |  |  | Aquarius | 267750 | 220515.2 | 2022-12-31 | Actual | 42957.6 | 42957.6 | 54454.4 | 52402.4

## finaance14
Month | 2023-01-01 | 2023-01-01 | 2023-02-02 | 2023-02-02 | 2023-03-03 | 2023-03-03 | 2023-04-04 | 2023-04-04 | 2023-05-05 | 2023-05-05 | 2023-06-06 | 2023-06-06
Jupiter2022 | 2593569 | 3903215 | 7214690 | 8333019 | 1503598 | 6941309 | 1932883 | 3764156 | 8885891 | 2905419 | 8341907 | 1630553
CloudOps2022 | 8227902 | 7482201 | 1355082 | 4723514 | 1209551 | 7070674 | 6263465 | 6406778 | 2365284 | 8806132 | 4911758 | 2060200
Sapphire2022 | 1440150 | 9147128 | 9084323 | 9224676 | 1384420 | 7085824 | 2550854 | 6469572 | 9522673 | 1446554 | 4835872 | 1562590
BrooklynAndBridge2022 | 7275756 | 3093372 | 5408438 | 6400078 | 6207510 | 9377402 | 5572788 | 2784879 | 3983841 | 4809248 | 2355651 | 6423624
CapEx2022 | 8874232 | 7760701 | 6043787 | 2322057 | 2796630 | 7130883 | 8712734 | 6192059 | 7447300 | 4425752 | 3270241 | 4252237
A3.11 2022 | 9416463 | 6571951 | 9104663 | 5346094 | 9611478 | 5297817 | 5729546 | 1053928 | 8224113 | 4498728 | 1388129 | 9249688
GeminiFW2022 | 1680389 | 3109669 | 2380638 | 4127588 | 5991124 | 9045060 | 4633478 | 7691996 | 6651348 | 6295879 | 1841611 | 6350311
JupiterFW2022 | 2001008 | 1412557 | 4441867 | 8127511 | 1064612 | 9107171 | 1489988 | 7947779 | 3657688 | 6306020 | 4420439 | 6959563
BrooklynAndBridge2022-2ndSOW | 7697765 | 6695770 | 3459880 | 7114144 | 3077986 | 9270911 | 3739759 | 8005901 | 4033310 | 2114557 | 1955614 | 2088197
Sapphire2022-2ndSOW | 4621122 | 7192150 | 5650878 | 1115515 | 3857910 | 3071372 | 2785102 | 7880092 | 3519910 | 1428835 | 6197886 | 3794595
Jupiter2022-2ndSOW | 5088094 | 1006762 | 9468444 | 8702263 | 1777360 | 5840340 | 9790022 | 9035624 | 6814118 | 3973185 | 8400395 | 5208109
CloudOps2022-2ndSOW | 3712654 | 7024700 | 4332681 | 3260548 | 2067688 | 4962207 | 1544149 | 3837739 | 7719376 | 7570238 | 3503497 | 9387244
Capex2022-2ndSOW | 7536095 | 2239486 | 8360107 | 1055864 | 5802169 | 1267443 | 9328073 | 4053475 | 9537787 | 1930324 | 9291297 | 7811159
MobileOps_SustAndMtktgExpansion | 3009289 | 4058665 | 5769648 | 2793496 | 3472243 | 2481395 | 2668460 | 3918162 | 7302503 | 9668403 | 9222876 | 5302266
MobileOps_Gemini | 4237655 | 8612203 | 8282895 | 5920947 | 3533523 | 6559597 | 3038035 | 2285777 | 3599553 | 2401855 | 5491278 | 8801265
BrooklynAndBridge2022-3rdSOW | 8166249 | 4801758 | 6945674 | 2016492 | 6945568 | 9754445 | 4665548 | 9040709 | 9119120 | 4620611 | 3453875 | 7480310
JupiterFW2022-2 | 7468744 | 4966505 | 7831526 | 8320768 | 1152822 | 7480930 | 9344190 | 9162784 | 3180251 | 5631205 | 1512243 | 4290192
Jupiter2022-2ndSOW-LBE3 | 9221011 | 9178599 | 1506146 | 4493631 | 1455055 | 7471438 | 2883211 | 2705722 | 5881259 | 7824483 | 8718702 | 6546227
IonicRF | 8777956 | 6987601 | 5267431 | 7323788 | 1925663 | 4126705 | 3773874 | 8763364 | 2996355 | 6958724 | 4878228 | 4685382
IPT | 8664173 | 9970408 | 3874416 | 1615974 | 8436616 | 8908061 | 3171997 | 5489894 | 5616605 | 5478356 | 2897069 | 9749408
EUMDR | 4435733 | 2219135 | 7810459 | 3423196 | 1122559 | 1153943 | 3918845 | 3869277 | 6257029 | 2030354 | 9880863 | 1569590
GMI | 8960248 | 9310681 | 5827575 | 5876284 | 6450486 | 8984249 | 4985714 | 4820500 | 4172216 | 5669697 | 2768014 | 7105358
Onsite Test Support(Mobile Ops) | 6398628 | 1535250 | 6406457 | 4916589 | 4254976 | 4227974 | 6067980 | 1510856 | 6772048 | 3450708 | 3952889 | 6126011
AQA Support( A3.11 Aquarius) | 8549108 | 2009376 | 1008419 | 9111718 | 4578278 | 1923479 | 4293338 | 2970290 | 3929143 | 3920621 | 8374295 | 8300779

## Login
user name | password | role
PROG-LEADER | welcome321 | 1 | GDC | delivery head
DVP | welcome321 | 2 | DVP
user3 | welcome321 | 3 | functional leader

## executive-bussiness
Month | Program Name | Budget | Resources | Schedule | Overall Health | Key Messages | Milestones | Risk /Issues | Quality Metrics er | Performance Metrics Re | Training Compliance Jupiter
2022-12-23 | Brooklyn | As per projection | No Open positions | As per Schedule | green | dummy text | dummy text | dummy text | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-24 | Sapphire | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-25 | Gemini | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-26 | Janus | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-27 | Aquarius | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-28 | ORCA 2.0 | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-29 | Operations | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-29 | Operations | As per projection | No Open positions | As per Schedule | green | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue
2022-12-30 | Jupiter | Under utilised | Open positions Greater than 1 month | Behind Schedule | red | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | << Free Text>> | No resources with Training overdue